## Project tasks
Project name | RAC Proj Plan
Plan owner | Austin Kiec
Project start date | 2025-07-02 08:00
Project finish date | 2026-02-27 17:00
Duration | 390 days
% complete | 9%
Exported on | 2025-08-22 15:03
Task number | Outline number | Blueprint ID | Name | Assigned to | Labels | # of months out | Finish | Department | Bucket | % complete | Priority | SummaryT | Start | Depends on | Dependents (after) | Effort | Effort completed | Effort remaining | Duration | Milestone | Notes | Completed | Checklist Items | Sprint | Goal | Description | Task Description | Contingency items | Assigned To
1 | 1 | OPS-35 | EOO/AGM Review Residency Documents to Finalize prior to submission DHS | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Review and edit Resident Handbooks with relevant details about services, environment and expectations for each Program Type Review and provide feedback on Resident Agreements specifically related to CATV provided or not, Phone service provided or not, and | Budget or Proforma revenue expectations established
2 | 2 | OPS-36 | AGM & EOO to Review Residence Documents | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Operations | Not Started | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | AGM & EOO review Residency Agreements for program elements to be included with R&B rates (CATV, Phone, Laundry) and Contact information on Addendum F ~p.23 Review Charges Manuals for pricing accuracy and program elements Review Resident Handbooks for deta | The Residency Documents need to be completed and posted
3 | 3 | WELL-104 | Apply for CLIA Waiver and Clinical Lab Permit | Miranda Coulter | 1 Month Prior | 1 | 2025-08-01 17:00 |  | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | WOS/AGM/EOO - Submit application for CLIA and CLP so that we can accomplish blood sugar checks, urine collection/UA, etc.
4 | 4 | TECH-01 | Evaluate Inventory of computer equipment to assess needs for ICC technology approach | ICC Admin |  |  |  | Technology | Not Started | 0% | Medium | yes | [7 empty] | No |  |  |  | Backlog
5 | 5 | TECH-02 | Cost estimate to be provided for needed equipment and network implementation for all Technology Related Vendors | ICC Admin |  |  |  | Technology | Not Started | 0% | Medium | yes | [7 empty] | No |  |  |  | Backlog
6 | 6 | TECH-03 | □ Computers |  |  |  |  | Technology |  | 0% | Medium | yes | [7 empty] | Yes | [6 empty] | All-in-one and laptop computers for managers, shared positions, and systems support
7 | 6.1 | TECH-04 | □ Fax, Scan, Printers | Maureen Battin |  |  |  | Technology | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog |  |  | Coordinate with printer vendor to order & deploy leased printer/scanner/fax machine(s)
8 | 6.2 | TECH-05 | □ Devices | ICC Admin |  |  |  | Technology | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog
9 | 6.3 | TECH-06 | □ Telecom | ICC Admin |  |  |  | Technology | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog
10 | 6.4 | TECH-07 | □ Desktop | ICC Admin |  |  |  | Technology | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog
11 | 6.5 | TECH-08 | □ Network | ICC Admin |  |  |  | Technology | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog
12 | 6.6 | TECH-09 | □ Mobile | Faith Richards |  |  |  | Technology | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog
13 | 6.7 | TECH-10 | □ Tablet | ICC Admin |  |  |  | Technology | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog
14 | 6.8 | TECH-11 | □ Domain Name | ICC Admin |  |  |  | Technology | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog |  |  | Transfer domain ownership and registration
15 | 6.9 | TECH-12 | Formulate Tech Costs for initial set up and on-going for MRM, and others | ICC Admin |  |  |  | Technology | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog
16 | 7 | TECH-13 | Ensure ISP contract includes at least 1gb/s download for the whole community |  |  |  | 2025-07-02 17:00 | Technology |  | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No | [6 empty] | We do need static IP address(es). we don't need a dedicated fiber line, we don't want to charge access out to residents individually
17 | 7.1 | TECH-14 | Ensure WiFi design specifications set sensitivity is at minimum -60 dBm throughout the entire community | ICC Admin |  |  |  | Technology | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog
18 | 7.2 | TECH-15 | Ensure WiFi sensitivity is at minimum -60 dBm throughout the entire community | ICC Admin |  |  |  | Technology | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog
19 | 7.3 | TECH-16 | Ensure needed networks exist | ICC Admin |  |  |  | Technology | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog |  |  | Integracare, Integacare-Guest, IntegraCare-Quickmar
20 | 7.4 | TECH-17 | Ensure various vendors work with the network vendor to ensure success in their areas of responsibility | ICC Admin |  |  |  | Technology | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog |  |  | Other systems needing wired or wifi connectivity can include door access, video phones for doors, and resident wander management; all of which would need coordinated between the installing/managing vendor and the network vendor. HWTE and RCR are examples
21 | 7.5 | MNT_HSK-01 | Housekeeping, Laundry create a status & needs list. | Paul Martin | 4 Months Prior | 4 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
22 | 8 | MNT_HSK-02 | □ Equipment - Large |  | 4 Months Prior | 4 | 2025-07-02 17:00 | Maintenance/Housekeeping |  | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 48 hours | 48 hours | 0 hours | 1 day | No | [6 empty] | Washers, Dryers, PTACS, Fridges, Hot water heaters, HVAC units, Walk-in Freezer & cooler, Dishwashers, Stoves, reach-in freezer & cooler, Snow blower, vehicle, etc.
23 | 8.1 | MNT_HSK-03 | □ Equipment - Small | Paul Martin | 4 Months Prior | 4 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Vacuum, carpet extractor, floor machine, water extractor, Hospitality cart, toaster,mixer, robocoup, microwaves, etc.
24 | 8.2 | MNT_HSK-04 | □ Linens - Inventory | Paul Martin | 4 Months Prior | 4 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | As per the ICC standards (COSM)
25 | 8.3 | MNT_HSK-05 | □ Cleaning Chemicals | Paul Martin | 4 Months Prior | 4 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
26 | 8.4 | MNT_HSK-06 | □ Cleaning Supplies | Paul Martin | 4 Months Prior | 4 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Mop, bucket, microfibers, duster,toilet brush, etc.
27 | 8.5 | MNT_HSK-07 | □ Hospitality Suppllies | Paul Martin | 4 Months Prior | 4 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | toilet paper, papertowels,garbage bags, etc.
28 | 8.6 | MNT_HSK-08 | Maintenance Inventory create a status & needs list | Paul Martin | 4 Months Prior | 4 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
29 | 9 | MNT_HSK-09 | □ Tools |  | 4 Months Prior | 4 | 2025-07-02 17:00 | Maintenance/Housekeeping |  | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 24 hours | 24 hours | 0 hours | 1 day | No
30 | 9.1 | MNT_HSK-10 | □ Supplies | Paul Martin | 4 Months Prior | 4 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | batteries, lightbulbs, outlets&covers,toilet flappers, lightswitches & covers, toilet handles, spray lube (WD40), can smoke, caulk, paint, paintbrushes and rollers, etc
31 | 9.2 | MNT_HSK-11 | □ Equipment | Paul Martin | 4 Months Prior | 4 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | shovels, electric testers, pressure washer, shopvac, hepavac, toilet snake, etc
32 | 9.3 | MNT_HSK-12 | Schedule Vendor Tours of all new equipment | Paul Martin | 1 Month Prior | 1 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
33 | 10 | MNT_HSK-13 | HVAC |  | 1 Month Prior | 1 | 2025-12-01 17:00 | Maintenance/Housekeeping |  | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 2160 hours | 0 hours | 2160 hours | 109 days | No | [6 empty] | Should receive manual from vendor & PM schedule
34 | 10.1 | MNT_HSK-14 | Sprinklers | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Should receive manual from vendor & PM schedule
35 | 10.2 | MNT_HSK-15 | Fire panel | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Should receive manual from vendor & PM schedule
36 | 10.3 | MNT_HSK-16 | Nurse call system | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Should receive manual from vendor & PM schedule
37 | 10.4 | MNT_HSK-17 | Wanderguard System | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Should receive manual from vendor & PM schedule
38 | 10.5 | MNT_HSK-18 | Ansul | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Should receive manual from vendor & PM schedule
39 | 10.6 | MNT_HSK-19 | Access control | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Should receive manual from vendor & PM schedule
40 | 10.7 | MNT_HSK-20 | Generator | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Should receive manual from vendor & PM schedule
41 | 10.8 | MNT_HSK-21 | Set up quarterly review of major systems to see which ones are coming up on 1 year install date | Paul Martin | 3 Months Post | -3 | 2025-12-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 872 hours | 0 hours | 872 hours | 109 days | No |  |  |  | Backlog |  |  | Warranty inspection by each vendor; detail should be in TELs
42 | 11 | MNT_HSK-22 | Schedule Fire and Life Safety Inspection | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Bob Mueller
43 | 12 | MNT_HSK-23 | Contact Info for all construction Vendors (to refer back to in case of mechanical questions) | Paul Martin | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
44 | 13 | MNT_HSK-24 | TELS | Paul Martin | 1 Month Prior | 1 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
45 | 14 | MNT_HSK-25 | Add community to TELS |  | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping |  | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 928 hours | 0 hours | 928 hours | 24 days | No | [6 empty] | Send request to Direct Supply to add new building to TELS
46 | 14.1 | MNT_HSK-26 | Create Users | ICC Admin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Add CEA, EOO, SME, HEA + work order profile
47 | 14.2 | MNT_HSK-27 | Create Tasks | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Setup of preventative maintenance and regulatory tasks
48 | 14.3 | MNT_HSK-28 | Asset Tag of equipment | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | DS asset tags all equipment & furniture; ICC adds the asset tag. Anything from pre-order opening list we will need to manually asset tag.
49 | 14.4 | MNT_HSK-29 | Add all areas for W/O and unit turns | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog
50 | 14.5 | MNT_HSK-30 | All Documentation entered with warranty dates | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog
51 | 14.6 | MNT_HSK-31 | EDP | Paul Martin | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
52 | 15 | MNT_HSK-32 | Create Standard |  | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping |  | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 32 hours | 0 hours | 32 hours | 1 day | No | [6 empty] | Work w/ EOO and SME to create binder per ICC Standard (COSM)
53 | 15.1 | MNT_HSK-33 | Maglock letter | Paul Martin | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
54 | 15.2 | MNT_HSK-34 | Master shutoffs w/ pictures | Paul Martin | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
55 | 15.3 | MNT_HSK-35 | Letter from Local authority certifying local compliance | Paul Martin | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
56 | 15.4 | MNT_HSK-36 | OHSA protocols - Lock-out/Tag-Out/ SDS/ COVID ETS | Paul Martin | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
57 | 16 | MNT_HSK-37 | Lock-out/Tag-out |  | 2 Months Prior | 2 | 2025-07-02 17:00 | Maintenance/Housekeeping |  | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 24 hours | 0 hours | 24 hours | 1 day | No
58 | 16.1 | MNT_HSK-38 | Create SDS Binders for appropriate areas in the community | Paul Martin | 2 Months Prior | 2 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
59 | 16.2 | MNT_HSK-39 | COVID Protocal | Paul Martin | 2 Months Prior | 2 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
60 | 16.3 | MNT_HSK-40 | Trainings | Paul Martin | 2 Months Prior | 2 | 2025-07-02 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
61 | 17 | MNT_HSK-41 | Department trainings |  | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping |  | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 32 hours | 0 hours | 32 hours | 1 day | No | [6 empty] | To include, at a minimum, walk through of the building
62 | 17.1 | MNT_HSK-42 | Company (ICC) trainings | Paul Martin | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
63 | 17.2 | MNT_HSK-43 | TELS Training | Paul Martin | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
64 | 17.3 | MNT_HSK-44 | GO Training | Paul Martin | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
65 | 17.4 | MNT_HSK-45 | Fire and Life Safety Train the Trainer | Paul Martin | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
66 | 18 | MNT_HSK-46 | FF&E | Paul Martin | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
67 | 19 | MNT_HSK-47 | Deliveries/ Shipping date validation |  | 2 Months Prior | 2 | 2025-08-01 17:00 | Operations |  | 46% | Medium | yes | 2025-07-01 09:00 |  |  | 200 hours | 92 hours | 108 hours | 24 days | No
68 | 19.1 | MNT_HSK-48 | Storage security | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
69 | 19.2 | MNT_HSK-49 | Department Distribution | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
70 | 19.3 | LIC-01 | Application for Certificate of Compliance | Megan Campbell | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 92 hours | 92 hours | 23 days | No |  |  |  | Backlog
71 | 20 | LIC-02 | Form 633 to be completed (Application) |  | 1 Month Prior | 1 | 2025-09-01 17:00 | Operations |  | 68% | Medium | yes | 2025-01-20 09:00 |  |  | 5480 hours | 3668 hours | 1812 hours | 161 days | No | [6 empty] | 1. Application for Certificate of Compliance.pdf
72 | 20.1 | LIC-12 | DHS Notification = Application Submission | Megan Campbell | Week of Acquisition | 0 | 2025-09-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | OK to send via email with Check over-night
73 | 20.2 | LIC-13 | →DHS Processes / Approve Application | Megan Campbell | Week of Acquisition | 0 | 2025-09-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 352 hours | 0 hours | 44 days | No |  |  |  | Backlog |  |  | Coordinate and Communicate w/ DHS (Kachmar, Jill ) via e-mail
74 | 20.3 | LIC-14 | Policy Submission: Prior to Scheduling Initial Inspection / After Receipt of Approval of Form 633 | Megan Campbell | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | 4a. 2600 - Personal Care Homes - Policy Review List.pdf | Receipt of Approved Form 633
75 | 20.4 | LIC-15 | □ Documentation of Education / Training of the current EOO - obtain from current operator | Shannon Joyce | 4 Months Prior | 4 | 2025-05-01 17:00 | Human Resources | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Proof of Education/Certification/Licenses/Continuing ED./ DHS Test from Current Owner (DD Request)
76 | 20.5 | LIC-16 | □ Current Criminal history / background checks for the owner/operator, Administrator and each currently hired person - H/R obtains | Shannon Joyce | 4 Months Prior | 4 | 2025-05-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | HR to conduct background checks for the submission, scan to Ops Admin for packet (Typically on ICC FIRST/SECOND VISIT)
77 | 20.6 | LIC-17 | □ Staffing Pattern / Shifts / Duties of hired and to-be-hired staff - Obtain data from current operator (payroll records): | Belinda Mcquaide | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | We interpret this from payroll records / Position Control Data (DD)
78 | 20.7 | LIC-18 | □ Ops develops Staffing Pattern from what exists, enter into Template | Belinda Mcquaide | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Complete Template demonstrating compliance w/ staffing requirement
79 | 20.8 | LIC-19 | 5. ICC Staffing Hours - MASTER.xlsx | Megan Campbell, Bobbi Olson | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-07-02 09:00 |  |  | 368 hours | 184 hours | 184 hours | 23 days | No |  |  |  | Backlog
80 | 20.9 | LIC-20 | □ CBC Policies for hiring of Future personnel | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
81 | 20.10 | LIC-21 | □ Educational and Training qualification of staff to be hired | Megan Campbell | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 92 hours | 92 hours | 23 days | No |  |  |  | Backlog |  |  | Current COSM p&p
82 | 20.11 | LIC-22 | □ Staff Training Plan for first 12-mos of operation | Faith Mong, Shannon Joyce | 4 Months Prior | 4 | 2025-05-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 16 hours | 0 hours | 16 hours | 1 day | No |  |  |  | Backlog |  |  | Current Year Training Plan w/ Training Resrouces
83 | 20.12 | LIC-23 | □ Floor plan/layout of all floors, clearly indicating exit paths and exits doors. Floor plan indicates the size of each bedroom, inluding ceiling height and all common areas. Floor plan indicate the number and location of each bathroom for staff and R's | Sarah Spardy | 4 Months Prior | 4 | 2025-05-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Current Ownership (DD Item) All Unit Types need to be represented with size of unit on the drawing
84 | 20.13 | LIC-24 | □ Elevator certificate of operation | Sarah Spardy | 4 Months Prior | 4 | 2025-05-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Vendor Provides (procure from DVL)
85 | 20.14 | LIC-25 | Policies & Procedures | Megan Campbell | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 92 hours | 92 hours | 23 days | No |  |  |  | Backlog
86 | 20.15 | LIC-26 | □ Reportable Incident Policy | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
87 | 20.16 | LIC-27 | □ Quality Management Plan | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
88 | 20.17 | LIC-28 | □ Resident Rights | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
89 | 20.18 | LIC-29 | □ Complaint Procedures | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
90 | 20.19 | LIC-30 | □ Pools, if applicable | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
91 | 20.20 | LIC-31 | □ Emergency Preparedness Plan | Megan Campbell, Paul Martin | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 16 hours | 8 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
92 | 20.21 | LIC-32 | □ Firearms and Weapons policy (if applicable) | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
93 | 20.22 | LIC-33 | □ Inoperable Fire Alarm / Smoke Detextor Policy | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
94 | 20.23 | LIC-34 | □ Emergency Medical Plan | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
95 | 20.24 | LIC-35 | □ Smoking Policy | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
96 | 20.25 | LIC-36 | □ Medication Administration Policy | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
97 | 20.26 | LIC-37 | □ Description of Services Policy | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
98 | 20.27 | LIC-38 | □ Discharge & Transfer Policy | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
99 | 20.28 | LIC-39 | □ Records (maintenance) Policy | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
100 | 20.29 | LIC-40 | Secured Dementia Units | Megan Campbell | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 92 hours | 92 hours | 23 days | No |  |  |  | Backlog
101 | 20.30 | LIC-41 | □ Environmental Protection Policy | Megan Campbell | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 92 hours | 92 hours | 23 days | No |  |  |  | Backlog |  |  | Current COSM p&p
102 | 20.31 | LIC-42 | □ Lock Approvals - documentation from current operator or owner | Sarah Spardy | 4 Months Prior | 4 | 2025-05-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Development from Construction from Vendor
103 | 20.32 | LIC-43 | 1. The type of locking system (a description for each door, and how it is secured and over-ridden, all components). This is typically a narrative | Sarah Spardy | 4 Months Prior | 4 | 2025-05-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Development from Construction from Vendor
104 | 20.33 | LIC-44 | 2. The operational description of the secured dementia care unit locking system of the doors | Sarah Spardy | 4 Months Prior | 4 | 2025-05-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Development from Construction from Vendor
105 | 20.34 | LIC-45 | 3. The manufacturer’s statement regarding the secured dementia care unit locking system = narrative on letterhead, this is how they function under normal and emergency contingency, and that they have been observed to function correctly | Sarah Spardy | 4 Months Prior | 4 | 2025-05-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Development from Construction from Vendor
106 | 20.35 | LIC-46 | 4. A written approval or a variance permitting locked exit doors from the Department of Labor & Industry, the Department of Health, or the appropriate local building authority | Sarah Spardy | 4 Months Prior | 4 | 2025-05-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Development from Construction from Vendor
107 | 20.36 | LIC-47 | □Verification of completion of additional training requirements for SDCU | Bobbi Olson, Megan Campbell | Week of Acquisition | 0 | 2025-09-01 17:00 | Development | Not Started | 50% | Medium |  | 2025-07-02 09:00 |  |  | 704 hours | 352 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | EOO provides verification of completion of additional training requirements of the team members they hire for MC. They are looking to see that the persons who will work in MC have the training, and of the people who have had the training, there are enough
108 | 20.37 | LIC-48 | □ Program Information | Megan Campbell | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-01-20 09:00 |  |  | 1120 hours | 1120 hours | 0 hours | 140 days | No |  |  |  | Backlog |  |  | Current COSM p&p
109 | 20.38 | LIC-49 | □ Staffing Pattern / Shifts | Bobbi Olson, Megan Campbell | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-01 09:00 |  |  | 16 hours | 16 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Operations determines staffing / places on a grid
110 | 20.39 | LIC-50 | 6. SDCU Staffing Schedule - MASTER.xlsx | Megan Campbell | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
111 | 20.40 | LIC-51 | □ General SDCU Information: 2600.239 (a), (c)(1)-(22) | Paul Martin, Megan Campbell | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-07-02 09:00 |  |  | 368 hours | 184 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Narrative from current operator or our observation during viist
112 | 20.41 | LIC-52 | □ Residency Agreement & Associated Documents | Bobbi Olson, Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 16 hours | 8 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Current ICC Agreement & Related Documents
113 | 20.42 | LIC-53 | □ Statement of Policy 2600.25 (e) - (f); 2600.109(a), (d) | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | covered in Residency Agreement
114 | 20.43 | LIC-54 | □ Resident Rights Poster | Megan Campbell | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 184 hours | 0 hours | 23 days | No |  |  |  | Backlog |  |  | covered in Residency Agreement
115 | 20.44 | LIC-55 | □ Fire Drill Record | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Use current P&P, plus state form (Forms ALL)
116 | 20.45 | LIC-56 | □ Pre-Admission Screening Form | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | DHS Form, provided by Ops
117 | 20.46 | LIC-57 | □ Assessment Form | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | ICC Form, provided by Ops
118 | 20.47 | LIC-58 | □ Support Plan Form | Megan Campbell | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 184 hours | 0 hours | 23 days | No |  |  |  | Backlog |  |  | DHS Form, provided by Ops
119 | 20.48 | LIC-59 | □ Medication Administration Record | Veronica Graham, Megan Campbell | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 368 hours | 368 hours | 0 hours | 23 days | No |  |  |  | Backlog |  |  | Blank from Pharmacy
120 | 20.49 | LIC-60 | □ Compliance with Fire Retardant Mattress requirement 2600.101(j)1 | Paul Martin, Megan Campbell | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-01 09:00 |  |  | 16 hours | 16 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Current COSM p&p
121 | 20.50 | LIC-61 | □ Civil Rights Compliance Letter (is dependent on completion of CR Questionnaire above) | Megan Campbell | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 92 hours | 92 hours | 23 days | No |  |  |  | Backlog |  |  | 3. CRCQ-Form_New-Fillable-Blank.pdf
122 | 20.51 | LIC-62 | □ Documentation of Homes' water source - ie., current water bill | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Ownership Provides during Due Diligence
123 | 20.52 | LIC-63 | □ Documentation showing the Home's sewer source | Paul Martin, Megan Campbell | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-07-01 09:00 |  |  | 16 hours | 8 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Ownership Provides during Due Diligence
124 | 20.53 | LIC-64 | □ List of the Home's legal entity listing of all licensed human service facilities, incl. parent companies, subsidiaries, parnerships, management agreements | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | ICC Admin has this listing on file - has license #s, Contact Info & EIN
125 | 20.54 | LIC-65 | □ Affidavit for the sale of a legal enetity that is currently operating pending appeal of a Department enforcement action or previous operator that was deemed not a responsible person by the Department | Sarah Spardy, Megan Campbell | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-01 09:00 |  |  | 16 hours | 16 hours | 0 hours | 1 day | No |  |  |  | Backlog
126 | 20.55 | LIC-03 | Guidance for Form 633 (Checklist) | Megan Campbell | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 92 hours | 92 hours | 23 days | No |  |  |  | Backlog |  |  | 2. DHS - Checklist for Initial Application Submission.pdf
127 | 21 | LIC-04 | □ Articles of Incorporation - copy of state's approved papers |  | 4 Months Prior | 4 | 2025-08-01 17:00 | Development |  | 93% | Medium | yes | 2025-05-01 09:00 |  |  | 240 hours | 224 hours | 16 hours | 67 days | No | [6 empty] | of/for the ownership entity
128 | 21.1 | LIC-05 | □ Fictitious Name Approval | Sarah Spardy | 4 Months Prior | 4 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | ppwk from the state
129 | 21.2 | LIC-06 | □ Foreign Business (legal entity formed in state other than PA) | Sarah Spardy | 4 Months Prior | 4 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | ppwk from the state, if applicable
130 | 21.3 | LIC-07 | □ Occupancy Permit | Sarah Spardy | 4 Months Prior | 4 | 2025-05-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Original depicting current intended use / if any construction, most recent C of O applies
131 | 21.4 | LIC-08 | □ EIN Number | Sarah Spardy | 4 Months Prior | 4 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
132 | 21.5 | LIC-09 | □ Completion of Check Req based on # beds / current license | Megan Campbell | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 184 hours | 0 hours | 23 days | No |  |  |  | Backlog |  |  | Complete ICC Check Request
133 | 21.6 | LIC-10 | □ Completion of Form 633 Application with the above information | Megan Campbell | 4 Months Prior | 4 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Form 633 is the application. The above is necessary to complete
134 | 21.7 | LIC-11 | □ Completion of Form DHS Bureau of Equal Opportunity Form HS Civil Rights Compliance for New Entity | Megan Campbell | 1 Month Prior | 1 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | 3. CRCQ-Form_New-Fillable-Blank.pdf
135 | 21.8 | LIC-66 | DHS Policy Phase Submission of Packet | Megan Campbell | 1 Month Prior | 1 | 2025-05-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog
136 | 22 | LIC-67 | →DHS Processes Policy Submission and Schedules On-Site Inspection | Megan Campbell | Week of Acquisition | 0 | 2025-09-01 17:00 | Operations | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 352 hours | 352 hours | 0 hours | 44 days | No |  |  |  | Backlog
137 | 23 | LIC-68 | →DHS Schedules On-Site | Megan Campbell | 1 Month Post | -1 | 2025-10-01 17:00 | Operations | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | allow 90 days from initial submission of Form 633 (above)
138 | 24 | OPS-00 | Begin monthly status update calls | Belinda Mcquaide | 8 Months Prior | 8 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | EOO and Home Office begin status updates. Teams calls for construction and sales updates
139 | 25 | OPS-01 | Develop Deposit protocol | Larry Rouvelas | 8 Months Prior | 8 | 2025-01-31 17:00 | Marketing | Not Started | 0% | Medium | yes | 2025-01-31 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Develop deposit protocol and amounts for Priority and VIP
140 | 26 | OPS-02 | CRD to complete GO and all Mgmt Training | Shannon Joyce | 6 Months Prior | 6 | 2025-02-28 17:00 | Human Resources | In progress | 50% | Medium | yes | 2025-02-28 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Move N training, Paycor, Wellness, HR, all completed BEFORE opening
141 | 27 | OPS-03 | ASD, RWD, SME to complete all Mgmt Training | Butch Cassiday Jr, Bobbi Olson | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 368 hours | 0 hours | 368 hours | 23 days | No |  |  |  | Backlog
142 | 28 | OPS-04 | DED and LSD's complete all Mgmt Training | Butch Cassiday Jr, Bobbi Olson | 1 Month Prior | 1 | 2025-08-01 17:00 | Operations | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 368 hours | 0 hours | 368 hours | 23 days | No |  |  |  | Backlog
143 | 29 | OPS-05 | Community walk through | Bobbi Olson | 6 Months Prior | 6 | 2025-02-28 17:00 | Operations | Not Started | 0% | Medium | yes | 2025-02-28 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
144 | 30 | OPS-06 | Walk through the community 2-3x weekly |  | 6 Months Prior | 6 | 2025-05-30 17:00 | Operations |  | 0% | Medium | yes | 2025-02-28 09:00 |  |  | 16 hours | 0 hours | 16 hours | 66 days | No | [6 empty] | take pictures, bring to report on monthly calls
145 | 30.1 | OPS-07 | Note all punch list items | Bobbi Olson | 6 Months Prior | 6 | 2025-02-28 17:00 | Operations | Not Started | 0% | Medium |  | 2025-02-28 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
146 | 30.2 | OPS-08 | Recruitment for hourly team | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
147 | 31 | OPS-09 | Post jobs on all platforms |  | 3 Months Prior | 3 | 2025-07-01 17:00 | Operations |  | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 24 hours | 0 hours | 24 hours | 23 days | No | [6 empty] | Indeed, glassdoor, Linkedin
148 | 31.1 | OPS-12 | Complete Interviews | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
149 | 31.2 | OPS-13 | Hire team members | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
150 | 31.3 | OPS-14 | Hourly team in GO | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
151 | 32 | OPS-15 | Complete GO for ICC standards |  | 2 Months Prior | 2 | 2025-07-01 17:00 | Human Resources |  | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 32 hours | 0 hours | 32 hours | 1 day | No
152 | 32.1 | OPS-16 | Complete state specific training needs | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
153 | 32.2 | OPS-17 | Complete BTD training | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Life Stories | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
154 | 32.3 | OPS-18 | Enroll in SLU | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
155 | 32.4 | OPS-19 | Call System | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
156 | 33 | OPS-20 | Test Call System |  | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations |  | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 24 hours | 0 hours | 24 hours | 1 day | No | [6 empty] | Assure system works, calls are working within range, battery life is lasting
157 | 33.1 | OPS-21 | Test Access Control | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Assign and test all staff devices, test on all inside and outside doors
158 | 33.2 | OPS-22 | Train Staff | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
159 | 33.3 | OPS-23 | Preopening Drills | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
160 | 34 | OPS-24 | Conduct fire drill |  | 2 Months Prior | 2 | 2025-09-26 17:00 | Operations |  | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 704 hours | 0 hours | 704 hours | 86 days | No
161 | 34.1 | OPS-25 | Conduct missing resident drill | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
162 | 34.2 | OPS-26 | Conduct generator load bank test | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
163 | 34.3 | OPS-27 | Contract Set Ups | Bobbi Olson | 3 Months Prior | 3 | 2025-09-26 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 688 hours | 0 hours | 688 hours | 86 days | No |  |  |  | Backlog
164 | 35 | OPS-28 | Set up contract with lanscaper |  | 3 Months Prior | 3 | 2025-08-01 17:00 | Operations |  | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 232 hours | 0 hours | 232 hours | 46 days | No
165 | 35.1 | OPS-29 | Set up contractor with generator company | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
166 | 35.2 | OPS-30 | Set up food provider | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
167 | 35.3 | OPS-31 | Set up contract with snow removal | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
168 | 35.4 | OPS-32 | Set up contract with monitoring company | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
169 | 35.5 | OPS-33 | Set up contract with HVAC company | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
170 | 35.6 | OPS-34 | Set up refrigeration contract | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
171 | 35.7 | WELL-001 | Establish expectations of RWD Role | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Build strong foundation in RWD because expectations are reviewed in detail at the beginning of ICC leadership.
172 | 36 | WELL-002 | Review RWD Job Description |  | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness |  | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 552 hours | 0 hours | 552 hours | 23 days | No | [6 empty] | Review each with RWD of community to ensure understanding of role and ICC expectations.
173 | 36.1 | WELL-003 | Review Responsibilities of RWD with RWD | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Review each with RWD of community to ensure understanding of role and ICC expectations.
174 | 36.2 | WELL-004 | Review A Day In The Life of an RWD Document with RWD | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Review each with RWD of community to ensure understanding of role and ICC expectations.
175 | 36.3 | WELL-005 | COSM Training | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | EOOs and RWDs attending; this should be done w/in first 30-45 days
176 | 37 | WELL-006 | Forms Implementation | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | WOS to assist with implementation of ICC standard forms methodically during first 30 days of opening and monitor moving forward. Skin assessments, shower lists, MARs, physician orders, interdisciplinary notes, transfer summaries.
177 | 38 | WELL-007 | MoveN | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Ensure smooth transition to our MoveN platform. | MoveN
178 | 39 | WELL-008 | Move N Kickoff |  | 1 Month Prior | 1 | 2025-10-01 17:00 | Wellness |  | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 1088 hours | 4 hours | 1084 hours | 67 days | No | [6 empty] | WOS to facilitate MoveN implementation from the wellness perspective. | MoveN
179 | 39.1 | WELL-009 | Move N Prework and Green Light | Megan Campbell | 2 Months Prior | 2 | 2025-07-01 17:00 | Wellness | Not Started | 50% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Work with MoveN to establish account for new community and format to match ICC standard, issuing the green light when we are able to proceed to onboard the community in MoveN. | MoveN
180 | 39.2 | WELL-010 | Enter assessments in MoveN | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Allow 2 hours per assessment; community team to start with paper assessments so that data entry can occur in parallel. NOTE some of this timeline may decrease if we have access to data dump from previous electronic medical record. | MoveN
181 | 39.3 | WELL-011 | MoveN Documentation Training/Implementation | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Ensure working knowledge of the wellness part of MoveN by providing MoveN training. Review appropriate implementation by auditing assessments, carenotes, incidents, focus areas, and face sheets. | MoveN
182 | 39.4 | WELL-012 | Incident Report Training/MoveN Documentation (reportable vs non-reportable | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | WOS to train on incident report completion in MoveN to ICC COSM policy. Also process for reportables and the list of reportable occurrences. | MoveN
183 | 39.5 | WELL-013 | Staffing | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Create staffing templates and learn to navigate OnShift for the RWD.
184 | 40 | WELL-014 | Establish staffing pattern for opening and projected census growth. |  | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness |  | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 368 hours | 0 hours | 368 hours | 23 days | No | [6 empty] | Use ICC staffing standard to establish staff schedule.
185 | 40.1 | WELL-015 | OnShift training | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Provide onshift training to new users via HR/OnShift trainers and help page. | OnShift
186 | 40.2 | WELL-016 | Paper assessments initiatied | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | WOS will work to gain initial assessment of current residents. Will implement assessment forms for new admissions as well. Having paper assessments will allow the WOS to support data entry of the assessment into the MoveN platform. | MoveN
187 | 41 | WELL-017 | Vaccine Clinics | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Ensure completed by previous company, if in season. Ensure established in timeline if not in season.
188 | 42 | WELL-018 | Certifications | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Assess status and ensure proper trainings for CPR, First Aid, MA, and Diabetic.
189 | 43 | WELL-019 | CPR |  | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness |  | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 736 hours | 0 hours | 736 hours | 23 days | No | [6 empty] | Assess current status. Schedule training as needed. Ensure proper documentation maintained at community.
190 | 43.1 | WELL-020 | First Aid | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Assess current status. Schedule training as needed. Ensure proper documentation maintained at community.
191 | 43.2 | WELL-021 | Diabetic Training | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Assess current status. Schedule training as needed. Ensure proper documentation maintained at community.
192 | 43.3 | WELL-022 | MA | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Assess current status. Schedule training as needed. Ensure proper documentation maintained at community.
193 | 43.4 | WELL-023 | Assignment Sheets | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Train RWD and assist with implementation of ICC standard assignment sheets
194 | 44 | WELL-024 | Blood Glucose Testing Management | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Implement ICC standards for glucose testing equipment and protocols.
195 | 45 | WELL-025 | Glucometer |  | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness |  | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 368 hours | 0 hours | 368 hours | 23 days | No | [6 empty] | Assess for and establish (if needed) a process for reconciling each glucometer vs. qmar on a daily basis.
196 | 45.1 | WELL-026 | Bood glucose testing protocol training/implementation | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Ensure med pass team is aware of the testing protocol and that the ICC standard protocol has been implemented per COSM policy.
197 | 45.2 | WELL-027 | Wander Management | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Train RWD on ICC standards and wanderguard system. Also review missing person protocol.
198 | 46 | WELL-028 | Contracts | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Establish needed contracts for wellness
199 | 47 | WELL-029 | Medical Director Contract |  | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations |  | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 72 hours | 0 hours | 72 hours | 1 day | No | [6 empty] | Assess for effective medical director. Assist community to establish a new medical director if necessary.
200 | 47.1 | WELL-030 | Ancillary Providers | Miranda Coulter | 2 Months Prior | 2 | 2025-07-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Assess for effective relationship with ancillary providers. Support RWD to seek new relationships where needed. Establish service agreements where needed/appropriate.
201 | 47.2 | WELL-031 | Rehab | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Establish service agreement.
202 | 47.3 | WELL-032 | Medical Supply | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Establish service agreement.
203 | 47.4 | WELL-033 | Lab | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Establish service agreement.
204 | 47.5 | WELL-034 | Hospice | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Establish service agreement.
205 | 47.6 | WELL-035 | Home Health | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Establish service agreement.
206 | 47.7 | WELL-036 | Podiatry | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Establish service agreement.
207 | 47.8 | WELL-037 | McKesson Medical Supplies | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Application process; then Matt needed acccess and one additiona team lead needed access due to responsibilities
208 | 47.9 | WELL-038 | DHS Licensure prep | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Assure all of dept in compliance for final inspection prior to licensure to ensure smooth process of granting license.
209 | 48 | WELL-039 | QMAR Adoption | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Establish full adoption of QMAR. | Pharmacy
210 | 49 | WELL-040 | Migration to QMAR |  | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness |  | 0% | Medium | yes | 2025-05-01 09:00 |  |  | 192 hours | 0 hours | 192 hours | 67 days | No | [6 empty] | Work with pharmacy to establish date for full transition from current system/account to ICC QMAR account | Pharmacy
211 | 49.1 | WELL-041 | QMAR Kick off planning/training | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Meet with RWD and med pass team to orient to our QMAR account, expectations, and process. | Migr to QMAR
212 | 49.2 | WELL-042 | Pharmacy | Veronica Graham | 4 Months Prior | 4 | 2025-05-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Ensure smooth transition and adoption of ICC pharmacy process for optimal experience at the community level.
213 | 50 | WELL-043 | Provider/prescriber letter |  | 2 Months Prior | 2 | 2025-10-01 17:00 | Wellness |  | 0% | Medium | yes | 2025-05-01 09:00 |  |  | 2168 hours | 0 hours | 2168 hours | 110 days | No | [6 empty] | Facilitate letter to physician notifying of pharmacy and procedures. | Pharmacy
214 | 50.1 | WELL-044 | Pharmacy Education | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Facilitate training with pharmacy for the community team. WOS to attend. | Pharmacy
215 | 50.2 | WELL-045 | Intro Email of Pharmacy Contacts | Belinda Mcquaide | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Introduce RWD/EOO via email to key players/contacts at pharmacy. | Pharmacy
216 | 50.3 | WELL-046 | Pharmacy Route Times Document | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Pharmacy will communicate route times. WOS will orient RWD/med passers to process and expectations. | Pharmacy
217 | 50.4 | WELL-047 | Pharmacy transition document | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Letter to families to notify of pharmacy info. Consider hosting a family night with pharmacy reps present. | Pharmacy
218 | 50.5 | WELL-048 | Pharmacy | Veronica Graham | 4 Months Prior | 4 | 2025-05-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Assess process of current pharmacy. Establish steps needed for successful transition to ICC pharmacy. Ensure notice issued to current pharmacy. | Pharmacy
219 | 50.6 | WELL-049 | Pharmacy Contract | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Completed with copies returned | Pharmacy
220 | 50.7 | WELL-050 | Pharmacy Logistics Planning | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Plan for the when and how of pharmacy transition. | Pharmacy
221 | 50.8 | WELL-051 | Coordinate Med Cart Delivery | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Establish med cart delivery date. | Pharmacy
222 | 50.9 | WELL-052 | Mail order medication Families | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Communicate ICC policy surrounding outside pharmacy. Include as part of family night. | Pharmacy
223 | 50.10 | WELL-053 | Physician order tracking during transition (time depends on electronic or paper) | Veronica Graham | Week of Acquisition | 0 | 2025-09-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | Community to fax orders, demo, and insurance information to pharmacy for each resident at earliest point beyond when confirmed QMAR date is given.
224 | 51 | WELL-054 | End of Month Changeover documents | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | WOS train on changeover process and documents. Rotate out MARs on charts so that most recent 3 months are present, all prior filed in thin chart. Print after midnight on 1st of the month. Also print physician's orders for every resident and file in the em
225 | 52 | WELL-055 | Resident Demographics | Megan Campbell | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Audit for current status. Wellness will ensure data entry of wellness areas. Marketing will ensure data entry of admission information (all available). | MoveN
226 | 53 | WELL-056 | TB Test Staff | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Ensure compliance of TB tests for all staff. Ensure compliance of TB tests for residents per state regulations/ICC standards.
227 | 54 | WELL-057 | Establish DME/RASP Tracker | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | use audits of DMEs and RASPs to create tracker to ensure timely renewals at/ahead of due date.
228 | 55 | WELL-058 | Medical Charts | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Establish medical charts in compliance with ICC Standards.
229 | 56 | WELL-059 | Set up medical records storage area |  | 1 Month Prior | 1 | 2025-10-01 17:00 | Wellness |  | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 896 hours | 0 hours | 896 hours | 66 days | No | [6 empty] | Audit chart storage and ensure that it makes sense and functions well. Also ensure sufficient space, proper chart type, and dividers.
230 | 56.1 | WELL-060 | Establish Resident Charts | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Ensure charts are in proper order and contain all required documents that are of the ICC standard as well as proper chart and dividers. | chart supplies
231 | 56.2 | WELL-061 | Ensure community has a dummy medical chart for reference | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Ensure an ICC dummy chart is in place in wellness for the team to refer to as they work to bring the charts into compliance for order and content.
232 | 56.3 | WELL-062 | Documentation Training | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Ensure working knowledge of documentation per ICC standards. | MoveN
233 | 57 | WELL-063 | Establish self-admin tests and schedule | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Audit self medicating residents. Ensure all have done the ICC standard test and are scheduled out for quarterly self-admin competency testing.
234 | 58 | WELL-064 | Med Carts Set Up | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Set up med carts to ensure presence of narc box, pill crusher, pill crush pouches, med cups, graduated med cups, pharmacy sticker such as see MAR, changed order, etc., laptop, mouse, scanner, mouse pad, properly working keys, pen, sharpie, highlighter, pi | Med Cart and Supplies Delivery
235 | 59 | WELL-065 | Establish MA Training Binder | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Binder needs to contain certificate of train the trainer, diabetic educator, tab for each med passer, initial training paperwork, schedule and complete observations and maintain documentation here. Review process for referring a team member for medication
236 | 60 | WELL-066 | Audits | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Audit multiple areas to establish status and create plan to bring into compliance with ICC standards.
237 | 61 | WELL-067 | PPE Inventory |  | 1 Month Prior | 1 | 2026-02-27 17:00 | Wellness |  | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 7560 hours | 0 hours | 7560 hours | 173 days | No | [6 empty] | Assess current supply to ensure quantity sufficient in case of need for isolation of any ill residents.
238 | 61.1 | WELL-068 | Enabler/Side Rail Audit | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Audit for enablers/side rails. Audit for appropriate documentation of any found.
239 | 61.2 | WELL-069 | Audit med carts for cleanliness and compliance. | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Audit med carts for loose pills, expiration dates, narc compliance, open date compliance, and order vs. on hand compliance.
240 | 61.3 | WELL-070 | Audit MoveN Resident Decision for CPR/chart spine/facesheet/qmar match | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Assure resident's desired status is present and all locations match and that proper paperwork is in place for any DNRs.
241 | 61.4 | WELL-071 | Audit MoveN Diet List-established and current in dining with scheduled email to DED | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Audit diet list for accuracy. Audit food service to ensure most recent list is present. Audit MoveN to ensure scheduled email drop to EOO/RWD/DED on a routine basis. (likely weekly)
242 | 61.5 | WELL-072 | Audit and implement thin chart process | Veronica Graham | 6 Months Post | -6 | 2026-02-27 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 1384 hours | 0 hours | 1384 hours | 173 days | No |  |  |  | Backlog |  |  | Ensure place to file thin charts and review expectation for retention of documentation with RWD.
243 | 61.6 | WELL-073 | Audit for contraband in MC | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Assess staff knowledge of handling of contraband items in MC. Perform contraband audit in MC.
244 | 61.7 | WELL-074 | Audit O2 use | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Audit for residents on oxygen. Ensure proper holders/storage. Ensure No Smoking sign is present on door of each resident.
245 | 61.8 | WELL-075 | Sharps Audit | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Audit sharps containers on med carts, in resident rooms and anywhere else sharps containers are present. Assess that they are properly secured and not overfilled. Also assess sharps devices to ensure that they are all safety devices. Assist to transition
246 | 61.9 | WELL-076 | Wellness Equipment Audit | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Audit/survey wellness dept for any equipment needed/missing that would help them do their jobs easier/better. Gather ideas and commentary from RWD/staff. Communicate needs to the RWD/EOO/AGM.
247 | 61.10 | WELL-077 | Audit missed meds process | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Audit missed meds reports. Provide education to RWD on anything that is not meeting our expectations and ICC standard. | QMAR
248 | 61.11 | WELL-078 | Audit Facesheets | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Audit facesheets for completion per ICC standard. Report findings to RWD/CRD/EOO. | QMAR
249 | 61.12 | WELL-079 | DME's with process for timeliness | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Assess current resident charts for DME presence, completion, and accuracy. Seek to obtain any missing or any updates needed.
250 | 61.13 | WELL-080 | RASPs | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Assess current resident charts for RASP/ASP(or state appropriate tool) presence and appropriate signatures.
251 | 61.14 | WELL-081 | Establish emergency medical plan | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Assess any plan in place. Assist RWD to know process and get the transition to the ICC standard EMP into place.
252 | 62 | WELL-082 | Ensure monthly vitals scheduled in Qmar | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Audit QMAR for vitals assigned for each resident by the 10th of the month and divided among shifts. | QMAR
253 | 63 | WELL-083 | Ensure shower schedule and laundry schedule established and implemented | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Assess for schedules and that it aligns with current census. Ensure any additions/edits needed, are made.
254 | 64 | WELL-084 | Assessment training | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Train RWD on ICC standard assessment and how to enter in MoveN to ICC standard. | MoveN
255 | 65 | WELL-085 | Establish monthly wellness dept meetings | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Train RWD on departmental meeting and proper paperwork. Assist to schedule out for the year.
256 | 66 | WELL-086 | Mechanical Lifts | Veronica Graham | 4 Months Prior | 4 | 2025-05-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Ensure needs, arrival, training, and safety.
257 | 67 | WELL-087 | Ensure arrival of lifts |  | 4 Months Prior | 4 | 2025-08-01 17:00 | Wellness |  | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 192 hours | 0 hours | 192 hours | 24 days | No | [6 empty] | Assess for current lifts present in community. Ensure proper working order. Issue request for replacement to EOO/AGM if needed. Ensure arrival at community.
258 | 67.1 | WELL-088 | Train on lifts/equipment | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Ensure hands on training on all lifts/equipment present in house and sign-off/documentation for each team member on such. | lift delivery
259 | 67.2 | WELL-089 | Set up wellness center | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Set up work stations, laptops, chairs, stools, manuals, file cabinets, supplies storage, bulletin boards | equipment delivery
260 | 68 | WELL-090 | Mobility Management/Falls Prevention Program Implementation | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Train team on ICC mobility management/falls prevention. Work with RWD to implement program in community. Huddles, High Risk Fall Designation, interventions, documentation
261 | 69 | WELL-091 | Set up first aid kits | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Audit first aid kits. Ensure located in proper ICC standard locations. Ensure meet state regs for contents. Ensure nothing expired.
262 | 70 | WELL-092 | Immobiles list, special needs list, etc | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Establish immobiles list if not already in place. Establish special needs list if not already in place. Ensure process for communicating immobiles at least monthly to the fire dept.
263 | 71 | WELL-093 | Immunization documentation | Veronica Graham | 1 Month Post | -1 | 2025-10-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | Audit immunization documentation. Work on a plan to enter all vaccines into MoveN per ICC standard. | MoveN
264 | 72 | WELL-094 | Missing resident training | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Ensure all wellness team members are trained on the Code George Burns protocol as well as resident location awareness.
265 | 73 | WELL-095 | MC Training | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Ensure all wellness team members have had Behind the Door Training, completed the workbook and turned in the work book page and have the certificate on file.
266 | 74 | WELL-096 | Call Bells | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Establish firm foundation for call bell system and procedures.
267 | 75 | WELL-097 | Set up and train on call bell system |  | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness |  | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 552 hours | 0 hours | 552 hours | 23 days | No | [6 empty] | audit call bell system. Ensure all team members have been trained and know how to use it. | Call bell system installation
268 | 75.1 | WELL-098 | Train on ICC call bell initiative | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Review call bell initiative with RWD via callbell playbook.
269 | 75.2 | WELL-099 | Train on ICC call bell reports | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Review all reports and function on PBI call bells with RWD. Show report #7 Assignments and expectation to update by adding the names of each caregiver and then post every day.
270 | 75.3 | WELL-100 | COVID-19 and Respiratory Illness | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Follow current protocol via infection control playbook. Ensure team has the current guidance and understands the protocol.
271 | 76 | WELL-101 | Introduction to Outlook | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Ensure knowledge via return demonstration of proper use of outlook platform to ensure communication is open.
272 | 77 | WELL-102 | Introduction/Review of State Regs | Veronica Graham | 2 Months Prior | 2 | 2025-07-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Review version to use of state regs. Also review individual high focus regulations to ensure proper knowledge.
273 | 78 | WELL-103 | ICC Contacts and Responsibilities | Veronica Graham | 1 Month Prior | 1 | 2025-08-01 17:00 | Wellness | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Review contacts at ICC Home Office and their responsibilities so that the team knows the appropriate person to reach out to as things come up.
274 | 79 | PROC-04 | Financial service must provide information to set up contracts with vendors | Maureen Battin | 6 Months Prior | 6 | 2025-02-28 17:00 | Procurement | Not Started | 0% | Medium | yes | 2025-02-28 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Credit Application Information sheet provided by Financial Services is needed. | Entity, bank account
275 | 80 | PROC-05 | Set up community contracts | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Procurement | Not Started | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
276 | 81 | PROC-06 | Set up maintenance contract for elevator(s) |  | 3 Months Prior | 3 | 2025-05-30 17:00 | Procurement |  | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 32 hours | 0 hours | 32 hours | 1 day | No | [6 empty] | Find out manufacturer from John Stare; set up through HPSI
277 | 81.1 | PROC-07 | Set up generator maintenance contract | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Procurement | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Find out manufacturer from John Stare; set up through HPSI
278 | 81.2 | PROC-08 | Set up trash removal and recycling contract | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Procurement | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Set up through HPSI
279 | 81.3 | PROC-09 | Set up lawn care and snow removal contracts | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Procurement | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Work with new EOO as well to include local landscape bids; set up via HPSI
280 | 81.4 | PROC-10 | Add new community to Amazon list of communities | Maureen Battin | 3 Months Prior | 3 | 2025-05-30 17:00 | Procurement | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
281 | 82 | PROC-11 | Soap and Paper towel dispensers installed in resident bathrooms, public and work areas of building CWP team does install prior to occupancy permit. Organized by Paul and Steve | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog
282 | 83 | PROC-12 | Hospitality chemical dispensers for cleaning and laundry installed | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | CWP team does install prior to opening. Organized by Paul and Steve
283 | 84 | PROC-13 | Set up utilities | John Stare | 4 Months Prior | 4 | 2025-05-01 17:00 | Development | Not Started | 0% | Medium | yes | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
284 | 85 | PROC-14 | Set up phone service to main building |  | 4 Months Prior | 4 | 2025-07-01 17:00 | Development |  | 0% | Medium | yes | 2025-05-01 09:00 |  |  | 32 hours | 0 hours | 32 hours | 44 days | No | [6 empty] | Work with Frenkel to get phone contract for main building set up and signed
285 | 85.1 | PROC-15 | Set up internet service to main building | John Stare | 4 Months Prior | 4 | 2025-05-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Work with Frenkel to get internet contract for main building set up and signed
286 | 85.2 | PROC-16 | Set up cable service to main building | John Stare | 2 Months Prior | 2 | 2025-07-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Work with Frenkel to get cable contract for main building set up and signed
287 | 85.3 | PROC-17 | Coordinate coax cable install | John Stare | 4 Months Prior | 4 | 2025-05-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Work with Frenkel to ensure cabling is ordered and installed for servicing elevators and fire panels
288 | 85.4 | PROC-18 | Coordinate pre-opening order process | Maureen Battin | 4 Months Prior | 4 | 2025-05-01 17:00 | Procurement | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
289 | 86 | PROC-19 | Order tools and other maintenance supplies |  | 4 Months Prior | 4 | 2025-08-01 17:00 | Maintenance/Housekeeping |  | 0% | Medium | yes | 2024-09-02 09:00 |  |  | 936 hours | 0 hours | 936 hours | 240 days | No | [6 empty] | Review Aptura's operational equipment order for what is already being furnished. Vendors: HD Supply and Direct Supply
290 | 86.1 | PROC-20 | Order bedroom and bathroom linens for PC and Life Stories | Maureen Battin | 4 Months Prior | 4 | 2025-05-01 17:00 | Procurement | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Review Aptura's softgoods order to determine what is already being furnished by Direct Supply. Vendor: Phoenix
291 | 86.2 | PROC-21 | Hospitality list of equipment to order-includes vacs, floor equipment, cleaning carts, etc… | Maureen Battin | 4 Months Prior | 4 | 2025-05-01 17:00 | Procurement | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Vendor: Hillyard
292 | 86.3 | PROC-22 | Hospitality list of trash bags, paper towels, toilet paper, for opening. | Maureen Battin | 1 Month Prior | 1 | 2025-08-01 17:00 | Procurement | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog
293 | 86.4 | PROC-23 | Wellness list of supplies including bandages, incontinence products, etc.. | Maureen Battin | 4 Months Prior | 4 | 2025-05-01 17:00 | Procurement | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Vendor: McKesson
294 | 86.5 | PROC-24 | Administration prepares list of office Supplies and equipment | Maureen Battin | 4 Months Prior | 4 | 2025-05-01 17:00 | Procurement | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Vendor: Staples
295 | 86.6 | PROC-25 | Activities prepares list of games and activities supplies for SL and Life Stories programs | Maureen Battin | 4 Months Prior | 4 | 2025-05-01 17:00 | Procurement | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Vendor: Amazon
296 | 86.7 | PROC-27 | Set up weekly check in w/ EOO | Maureen Battin | 3 Months Prior | 3 | 2025-05-30 17:00 | Procurement | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Provide details of orders so the onsite team can verify delivery of all items.
297 | 86.8 | MKT-000 | Pre-Opening Development Marketing Meeting | Larry Rouvelas | 12 Months Prior | 12 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2024-09-02 09:00 |  |  | 704 hours | 0 hours | 704 hours | 88 days | No |  |  |  | Backlog
298 | 87 | MKT-001 | Conduct meeting to define scope of project to review floor plans, features and ammenities |  | 12 Months Prior | 12 | 2025-01-01 17:00 | Marketing |  | 100% | Medium | yes | 2025-01-01 09:00 |  |  | 40 hours | 40 hours | 0 hours | 1 day | No
299 | 87.1 | MKT-002 | Conduct market feasibility study and market analysis | Larry Rouvelas | 12 Months Prior | 12 | 2025-01-01 17:00 | Marketing | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
300 | 87.2 | MKT-003 | Indentify rates based on competitive analysis research | Larry Rouvelas | 12 Months Prior | 12 | 2025-01-01 17:00 | Marketing | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
301 | 87.3 | MKT-004 | Repeat market research- understand target audience, competitors and market trends | Larry Rouvelas, Bobbi Olson | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 16 hours | 16 hours | 0 hours | 1 day | No |  |  |  | Backlog
302 | 87.4 | MKT-005 | Architectural and Design Phase | Sarah Spardy | 12 Months Prior | 12 | 2025-01-01 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
303 | 88 | MKT-006 | Logo Development |  | 12 Months Prior | 12 | 2025-01-01 17:00 | Development |  | 100% | Medium | yes | 2025-01-01 09:00 |  |  | 24 hours | 24 hours | 0 hours | 1 day | No
304 | 88.1 | MKT-007 | Create Slideshow of renderings | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
305 | 88.2 | MKT-008 | Create renderings, rates and floor plans | Sarah Spardy | 10 Months Prior | 10 | 2025-01-01 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
306 | 88.3 | MKT-009 | Develop Branding and Marketing Materials | Larry Rouvelas | 10 Months Prior | 10 | 2025-01-01 17:00 | Marketing | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
307 | 89 | MKT-010 | Stationary, Business Cards Etc |  | 9 Months Prior | 9 | 2025-07-02 17:00 | Operations |  | 25% | Medium | yes | 2025-01-01 09:00 |  |  | 32 hours | 8 hours | 24 hours | 131 days | No
308 | 89.1 | MKT-011 | Develop and approive initial Collateral Pieces | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
309 | 89.2 | MKT-012 | Order Print Material | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
310 | 89.3 | MKT-013 | Create Community specific Initial Priority Reservation Form and Founders Club Incentives/Memberships | Larry Rouvelas | 10 Months Prior | 10 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
311 | 89.4 | MKT-014 | Signage | Sarah Spardy | 12 Months Prior | 12 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
312 | 90 | MKT-015 | Coming Soon Signage on Site |  | 12 Months Prior | 12 | 2025-07-02 17:00 | Development |  | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 24 hours | 24 hours | 0 hours | 1 day | No
313 | 90.1 | MKT-016 | Order Sandwich Boards | Sarah Spardy | 10 Months Prior | 10 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
314 | 90.2 | MKT-017 | Order Sales Center signage | Sarah Spardy | 10 Months Prior | 10 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
315 | 90.3 | MKT-018 | Website Development | Larry Rouvelas | 10 Months Prior | 10 | 2025-07-02 17:00 | Marketing | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
316 | 91 | MKT-019 | Website URL |  | 10 Months Prior | 10 | 2025-01-01 17:00 | Marketing |  | 0% | Medium | yes | 2025-01-01 09:00 |  |  | 56 hours | 0 hours | 56 hours | 1 day | No
317 | 91.1 | MKT-020 | Website QR Codes | Larry Rouvelas | 10 Months Prior | 10 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
318 | 91.2 | MKT-021 | Establish Community Phone Number(Rollover to HO & then EOO Cell) | John Stare | 10 Months Prior | 10 | 2025-01-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
319 | 91.3 | MKT-022 | Create Base Pages | ICC Admin | 10 Months Prior | 10 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
320 | 91.4 | MKT-023 | Populate Pages with Marketing Info | Larry Rouvelas | 10 Months Prior | 10 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
321 | 91.5 | MKT-024 | Develop Event Page | Larry Rouvelas | 10 Months Prior | 10 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
322 | 91.6 | MKT-025 | Virtual Tour Developed and Completed | Larry Rouvelas, Bobbi Olson | Week of Acquisition | 0 |  | Marketing | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog
323 | 91.7 | MKT-026 | Social Media Prescence | Larry Rouvelas, Bobbi Olson | 10 Months Prior | 10 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 16 hours | 0 hours | 16 hours | 1 day | No |  |  |  | Backlog
324 | 92 | MKT-027 | Establish business google listing |  | 10 Months Prior | 10 | 2025-01-01 17:00 | Marketing |  | 50% | Medium | yes | 2025-01-01 09:00 |  |  | 32 hours | 20 hours | 12 hours | 1 day | No
325 | 92.1 | MKT-028 | Create Social Media Plan and Set Up Social Media Portals (FB, Twitter, Instagram, NextDoor, Canva) | Larry Rouvelas, Bobbi Olson | 10 Months Prior | 10 | 2025-01-01 17:00 | Marketing | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 16 hours | 16 hours | 0 hours | 1 day | No |  |  |  | Backlog
326 | 92.2 | MKT-029 | Assign user id log in/ passwords for platforms | ICC Admin | 10 Months Prior | 10 | 2025-01-01 17:00 | Technology | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
327 | 92.3 | MKT-030 | CRM Development | Megan Campbell | 10 Months Prior | 10 | 2025-01-01 17:00 | Operations | Not Started | 50% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog
328 | 93 | MKT-031 | Notify Move N of need for Database initiation - need address, phone, point of contact |  | 10 Months Prior | 10 | 2025-07-02 17:00 | Operations |  | 1% | Medium | yes | 2025-01-01 09:00 |  |  | 712 hours | 8 hours | 704 hours | 131 days | No
329 | 93.1 | MKT-032 | Set up MoveN - need Unit Library for upload | Sarah Spardy | 7 Months Prior | 7 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
330 | 93.2 | MKT-033 | Provide MoveN Marketing Module training: EOO/CRD/CLD | Larry Rouvelas | 6 Months Prior | 6 | 2025-02-28 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 344 hours | 0 hours | 344 hours | 43 days | No |  |  |  | Backlog
331 | 93.3 | MKT-034 | Begin Data Entry | Larry Rouvelas | 6 Months Prior | 6 | 2025-02-28 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 344 hours | 0 hours | 344 hours | 43 days | No |  |  |  | Backlog
332 | 93.4 | MKT-035 | Complete all deposits abd pipeline tracking throgh CRM | Larry Rouvelas | 6 Months Prior | 6 | 2025-02-28 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-02-28 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
333 | 93.5 | MKT-036 | Marketing Module Log in Needs | ICC Admin | 10 Months Prior | 10 | 2025-01-01 17:00 | Technology | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
334 | 94 | MKT-037 | Create MoveN log in for EOO/CRD |  | 10 Months Prior | 10 | 2025-07-02 17:00 | Technology |  | 67% | Medium | yes | 2025-07-02 09:00 |  |  | 24 hours | 16 hours | 8 hours | 1 day | No
335 | 94.1 | MKT-039 | Canva Account- flyer creation w/ICC standards | ICC Admin | 6 Months Prior | 6 | 2025-07-02 17:00 | Marketing | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
336 | 94.2 | MKT-040 | Create CareFeed log in for EOO/CRD | Bobbi Olson | 2 Months Prior | 2 | 2025-07-02 17:00 | Technology | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
337 | 94.3 | MKT-041 | Monthly Drone Footage | Sarah Spardy | 12 Months Prior | 12 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
338 | 95 | MKT-042 | Ground Breaking Event |  | 10 Months Prior | 10 | 2025-07-02 17:00 | Marketing |  | 75% | Medium | yes | 2025-01-01 09:00 |  |  | 32 hours | 24 hours | 8 hours | 131 days | No
339 | 95.1 | MKT-043 | Identify date for ground breaking | Sarah Spardy | 11 Months Prior | 11 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
340 | 95.2 | MKT-044 | Create Ground breaking invite/audience | Larry Rouvelas | 10 Months Prior | 10 | 2025-07-02 17:00 | Marketing | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
341 | 95.3 | MKT-045 | Work with MH Media to execute event- to include rack cards creation, invites etc. | Larry Rouvelas | 10 Months Prior | 10 | 2025-07-02 17:00 | Marketing | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
342 | 95.4 | MKT-046 | Launch PR Campaign | Larry Rouvelas | 11 Months Prior | 11 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
343 | 96 | MKT-047 | Create and Outline Public Relations Plan |  | 11 Months Prior | 11 | 2025-01-01 17:00 | Marketing |  | 20% | Medium | yes | 2025-01-01 09:00 |  |  | 40 hours | 8 hours | 32 hours | 1 day | No
344 | 96.1 | MKT-048 | Filming and Recording for Television, Social Media and YouTube Outlets | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
345 | 96.2 | MKT-049 | Indentify Initial Advertsing Concept Development and Media Engagement | Bobbi Olson | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
346 | 96.3 | MKT-050 | Secure Pricing and Outlets | Bobbi Olson | 10 Months Prior | 10 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
347 | 96.4 | MKT-051 | Internal Sales Launch with Phone, Email and Organic Lead Bases(Sales Lead) | Bobbi Olson | 8 Months Prior | 8 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
348 | 96.5 | MKT-052 | Sales Center Monthly Rental | Sarah Spardy | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
349 | 97 | MKT-053 | Installation of Sales Center Items(Furniture, Fixtures, Phones) |  | 9 Months Prior | 9 | 2025-02-28 17:00 | Marketing |  | 14% | Medium | yes | 2025-01-01 09:00 |  |  | 56 hours | 8 hours | 48 hours | 43 days | No
350 | 97.1 | MKT-054 | Renderings and Floor Plans for Sales Center Completed and Displayed | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
351 | 97.2 | MKT-055 | Print Sales Promotional Flyers | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
352 | 97.3 | MKT-056 | Property Signage and Sales Center Signage Installation | Sarah Spardy | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
353 | 97.4 | MKT-057 | Track Sales Center Monthly Spend via Spend down | Bobbi Olson | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
354 | 97.5 | MKT-058 | Develop and Send Sales Office Grand Opening Direct Mailing | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
355 | 97.6 | MKT-059 | Create and send Emailer Teaser | Bobbi Olson | 6 Months Prior | 6 | 2025-02-28 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-02-28 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
356 | 97.7 | MKT-060 | Recruitment/Onboarding | Butch Cassiday Jr | 9 Months Prior | 9 | 2025-01-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
357 | 98 | MKT-061 | Hire Executive Director and Introduce to Key Players |  | 9 Months Prior | 9 | 2025-05-30 17:00 | Operations |  | 25% | Medium | yes | 2025-01-01 09:00 |  |  | 32 hours | 8 hours | 24 hours | 108 days | No
358 | 98.1 | MKT-062 | Hire CRD and Introduce to Key Players | Bobbi Olson | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
359 | 98.2 | MKT-063 | Review and establish expectations each with EOO/CRD to ensure understanding of role and ICC expectations. | Belinda Mcquaide | 6 Months Prior | 6 | 2025-02-28 17:00 | Ops Admin | Not Started | 0% | Medium |  | 2025-02-28 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
360 | 98.3 | MKT-064 | Sales Center Receptionist Hired | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
361 | 98.4 | MKT-065 | Develop and Print Family and Team Member Referral Flyers | Bobbi Olson, Larry Rouvelas |  |  |  |  | Not Started | 0% | Medium | [8 empty] | No |  |  |  | Backlog
362 | 98.5 | MKT-066 | Event Strategy | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
363 | 99 | MKT-067 | Sales Center Grand Opening |  | 9 Months Prior | 9 | 2025-07-01 17:00 | Marketing |  | 14% | Medium | yes | 2025-01-01 09:00 |  |  | 56 hours | 8 hours | 48 hours | 130 days | No
364 | 99.1 | MKT-068 | Post Referral and Prospect Event Pre-opening event outline | Bobbi Olson | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
365 | 99.2 | MKT-069 | Referral Source Video Campaign Launch | Bobbi Olson | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
366 | 99.3 | MKT-070 | Plan and Execute Prospect Events | Bobbi Olson | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 50% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog
367 | 99.4 | MKT-071 | Plan and Execute Referral Events | Bobbi Olson | 8 Months Prior | 8 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
368 | 99.5 | MKT-072 | Key Player Event | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
369 | 99.6 | MKT-073 | Host Memory Loss Support Group | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
370 | 99.7 | MKT-074 | Full Scale Launch of Grass Roots Direct Sales Efforts | Bobbi Olson | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 50% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog
371 | 100 | MKT-075 | Scheduling and Present Group Lunches |  | 9 Months Prior | 9 | 2025-08-01 17:00 | Marketing |  | 0% | Medium | yes | 2025-01-01 09:00 |  |  | 376 hours | 0 hours | 376 hours | 153 days | No
372 | 100.1 | MKT-076 | Referral Lunch and Presentation | Bobbi Olson | 1 Month Prior | 1 | 2025-08-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog
373 | 100.2 | MKT-077 | Finalize Guided Provider Network | Bobbi Olson | 1 Month Prior | 1 | 2025-08-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog
374 | 100.3 | MKT-078 | Sales and Marketing Quarterly Plan and Strategies | Bobbi Olson | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
375 | 101 | MKT-079 | Create a comprehensive plan including online and offline strategies: to include digital marketing, advertising, PR, and events |  | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing |  | 14% | Medium | yes | 2025-01-01 09:00 |  |  | 56 hours | 8 hours | 48 hours | 1 day | No
376 | 101.1 | MKT-080 | External Strategic Sales Begin with Referral Development (ED Lead) | Bobbi Olson | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
377 | 101.2 | MKT-081 | Identify Community Partnerships/Memberships via community outreach | Bobbi Olson | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
378 | 101.3 | MKT-082 | Identify Players for Guided Provider Network | Bobbi Olson | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
379 | 101.4 | MKT-083 | Identify sales channels, pricing strategy, and sales process | Bobbi Olson | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 50% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog
380 | 101.5 | MKT-084 | Identify Marketing strategies to include differentiators | Bobbi Olson | 8 Months Prior | 8 | 2025-01-01 17:00 | Marketing | Not Started | 50% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog
381 | 101.6 | MKT-085 | Order Giveaways | Bobbi Olson | 8 Months Prior | 8 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
382 | 101.7 | MKT-086 | Advertising | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
383 | 102 | MKT-087 | Finalization of Advertising for All Media |  | 9 Months Prior | 9 | 2025-07-01 17:00 | Marketing |  | 0% | Medium | yes | 2025-01-01 09:00 |  |  | 72 hours | 0 hours | 72 hours | 130 days | No
384 | 102.1 | MKT-088 | Cable TV | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
385 | 102.2 | MKT-089 | Internet | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
386 | 102.3 | MKT-090 | Outdoor | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
387 | 102.4 | MKT-091 | Print | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
388 | 102.5 | MKT-092 | Sponsorship(Alz Associaiton etc) | Larry Rouvelas, Bobbi Olson | 6 Months Prior | 6 | 2025-02-28 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-02-28 09:00 |  |  | 16 hours | 0 hours | 16 hours | 1 day | No |  |  |  | Backlog
389 | 102.6 | MKT-093 | Paid Social Media | Larry Rouvelas, Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 16 hours | 0 hours | 16 hours | 1 day | No |  |  |  | Backlog
390 | 102.7 | MKT-094 | Model Room Creation | Larry Rouvelas | 2 Months Prior | 2 | 2025-07-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
391 | 103 | MKT-095 | Direct Mail/Emailer/Personal Invitation for Model Apartment Grand Opening |  | 1 Month Prior | 1 | 2025-09-01 17:00 | Marketing |  | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 1240 hours | 0 hours | 1240 hours | 44 days | No
392 | 103.1 | MKT-096 | Model Apartment Setup | Sarah Spardy | Week of Acquisition | 0 | 2025-09-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog
393 | 103.2 | MKT-097 | Model Apartments Grand Opening (upon receipt of C of O) | Bobbi Olson | Week of Acquisition | 0 | 2025-09-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog
394 | 103.3 | MKT-098 | Dusty Shoe Tour | Bobbi Olson | Week of Acquisition | 0 | 2025-09-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog
395 | 103.4 | MKT-099 | Grand Opening | Larry Rouvelas | 1 Month Prior | 1 | 2025-08-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog
396 | 104 | MKT-100 | Direct Mail Grand Opening Invitation |  | 2 Months Prior | 2 | 2025-10-03 17:00 | Marketing |  | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 1280 hours | 0 hours | 1280 hours | 91 days | No
397 | 104.1 | MKT-101 | Mailing and Personal Invitations for Sneak Peak and Family/Referral Invitation (Small Group) | Larry Rouvelas | 2 Months Prior | 2 | 2025-07-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
398 | 104.2 | MKT-102 | Sneak Peak Grand Opening Key Players | Larry Rouvelas, Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 16 hours | 0 hours | 16 hours | 1 day | No |  |  |  | Backlog
399 | 104.3 | MKT-103 | Grand Opening Community | Bobbi Olson | Week of Acquisition | 0 | 2025-10-03 17:00 | Marketing | In progress | 0% | Medium |  | 2025-07-02 09:00 |  |  | 544 hours | 0 hours | 544 hours | 68 days | No |  | 0/1 | Schedule a date - tentative for 9/25/25 | Backlog
400 | 104.4 | MKT-104 | IL Grand Opening | Bobbi Olson | Week of Acquisition | 0 | 2025-09-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog
401 | 104.5 | MKT-105 | Facilatate the move-in process for initial depositors. | Bobbi Olson | Week of Acquisition | 0 | 2025-09-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog
402 | 104.6 | LSTO-01 | Begin volunteer recruitment | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Life Stories | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Complete background checks, register for GO/state specific training, put together binder with all volunteer information and orientation checklist.
403 | 105 | LSTO-02 | Begin Entertainment programs | Bobbi Olson | 1 Month Prior | 1 | 2025-08-01 17:00 | Life Stories | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Collect W-9s for all entertainers planning on coming to the community.
404 | 106 | LSTO-03 | Complete Actviity Calendar | Bobbi Olson | 1 Month Prior | 1 | 2025-08-01 17:00 | Life Stories | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Access, evaluate and complete Resident Activity Calendar. Adhere to ICC standards
405 | 107 | LSTO-04 | Order Supplies | Bobbi Olson | 4 Months Prior | 4 | 2025-05-01 17:00 | Life Stories | Not Started | 0% | Medium | yes | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Access and evaluate community supplies and accounts for vendors for activity supplies.
406 | 108 | LSTO-05 | BTD Training | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Life Stories | Not Started | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Complete Behind the door Training and review training materials. Complete mgmt specific BTD training and prepare binders for all new team members
407 | 109 | LSTO-06 | MC Chemical List | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Maintenance/Housekeeping | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | SDS specific to MC chemicals. Print and add all chemicals used in MC to the SDS binder and keep in MC neighborhood
408 | 110 | LSTO-07 | Life Story | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Life Stories | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Review LifeStory. Prepare to teach and complete LifeStory paperwork with all new families
409 | 111 | LSTO-08 | Recruitment for Assistant | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Life Stories | Not Started | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | If applicable, recruit for assistant. Place job opening on all job boards, interview for candidate, hire
410 | 112 | LSTO-09 | Pet Program | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Life Stories | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | If applicable, prepare pet program. Complete all ICC standard paperwork, put together binder that houses all vaccination records
411 | 113 | LSTO-10 | MC resident supplies | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Life Stories | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Assess accessibility to contrband - how is it stored. Assure there is a place for all MC personal products either in the rooms, separate closet, etc
412 | 114 | LSTO-11 | Missing resident drill | Bobbi Olson | 1 Month Prior | 1 | 2025-08-01 17:00 | Life Stories | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Complete and document missing resident drill. Complete drill using ICC standards, document and educate all team members
413 | 115 | LSTO-12 | Programs Supplies | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Life Stories | Not Started | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Order all supplies for programming. Order at least 1 quarter worth of programming supplies; baking, bingo, sensory, exercise, music, etc.
414 | 116 | LSTO-13 | Life Stations | Bobbi Olson | 4 Months Prior | 4 | 2025-05-01 17:00 | Life Stories | Not Started | 0% | Medium | yes | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Review and provide input for all Life Stations specific to community area. nuture station, garden station, bus stop, fidget area, music area, art, mans area, community and geographic specific stations added
415 | 117 | LSTA-01 | If applicable, recruit for assistant | Bobbi Olson | Week of Acquisition | 0 | 2025-09-01 17:00 | Life Stages | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | Place job on all platforms
416 | 118 | LSTA-02 | Get vehicle in order | Bobbi Olson | 4 Months Prior | 4 | 2025-05-01 17:00 | Life Stages | Not Started | 0% | Medium | yes | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
417 | 119 | LSTA-03 | Vehicle Registration |  | 4 Months Prior | 4 | 2025-08-01 17:00 | Life Stages |  | 0% | Medium | yes | 2025-05-01 09:00 |  |  | 216 hours | 0 hours | 216 hours | 67 days | No | [6 empty] | Assure vehicle registration is on hand and in current state
418 | 119.1 | LSTA-04 | Vehicle Insurance | Bobbi Olson | 4 Months Prior | 4 | 2025-05-01 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Assure current insurance policy onsite and at home office
419 | 119.2 | LSTA-05 | Vehicle Policies | Bobbi Olson | 4 Months Prior | 4 | 2025-05-01 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Review COSM and adhere to all vehicle policy
420 | 119.3 | LSTA-06 | Vehicle First Aid | Bobbi Olson | 4 Months Prior | 4 | 2025-05-01 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-05-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Order and install COSM specific first aid kit
421 | 119.4 | LSTA-07 | Vehicle go bag | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Prepare change of clothes, incontinence products and other COSM specific materials are in a bag and on the bus
422 | 119.5 | LSTA-08 | Begin Volunteer Program | Bobbi Olson | 1 Month Prior | 1 | 2025-08-01 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog
423 | 120 | LSTA-09 | Complete background checks |  | 1 Month Prior | 1 | 2025-08-01 17:00 | Life Stages |  | 1% | Medium | yes | 2025-07-02 09:00 |  |  | 376 hours | 4 hours | 372 hours | 23 days | No
424 | 120.1 | LSTA-10 | Register for GO/state specific training | Bobbi Olson | 1 Month Prior | 1 | 2025-07-02 17:00 | Life Stages | Not Started | 50% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog
425 | 120.2 | LSTA-11 | Put together binder with all volunteer information and orientation checklist | Bobbi Olson | 1 Month Prior | 1 | 2025-08-01 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog
426 | 120.3 | LSTA-12 | Assure pet policy is available | Bobbi Olson | 1 Month Prior | 1 | 2025-08-01 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog
427 | 121 | LSTA-13 | Put together binder with pet records for Pets on Wheels |  | 1 Month Prior | 1 | 2025-07-02 17:00 | Life Stages |  | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 32 hours | 32 hours | 0 hours | 1 day | No
428 | 121.1 | LSTA-14 | Leave tabs for space for commuity live in pets | Bobbi Olson | 1 Month Prior | 1 | 2025-07-02 17:00 | Life Stages | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
429 | 121.2 | LSTA-15 | Leave tabs for space for family pets who will be visiting | Bobbi Olson | 1 Month Prior | 1 | 2025-07-02 17:00 | Life Stages | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
430 | 121.3 | LSTA-16 | Assure per ICC standard/COSM policy | Bobbi Olson | 1 Month Prior | 1 | 2025-07-02 17:00 | Life Stages | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
431 | 121.4 | LSTA-17 | Access, evaluate and complete Resident Activity Calendar | Bobbi Olson | 1 Month Prior | 1 | 2025-07-02 17:00 | Life Stages | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
432 | 122 | LSTA-18 | Adhere to ICC standards |  | 1 Month Prior | 1 | 2025-07-01 17:00 | Life Stages |  | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No | [6 empty] | spiritual, sensory, outings, purposeful, engaging, musical. Look at COSM
433 | 122.1 | LSTA-19 | If applicable, train on programming technology | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
434 | 123 | LSTA-20 | Work with audio/video company for community theather |  | 2 Months Prior | 2 | 2025-07-01 17:00 | Life Stages |  | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 16 hours | 0 hours | 16 hours | 23 days | No | [6 empty] | Be there during install to undertand all euipment needs and process
435 | 123.1 | LSTA-21 | train self and team on programming technology | Bobbi Olson | 2 Months Prior | 2 | 2025-07-01 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Life Loop, IN2L, Lucynt, etc
436 | 123.2 | LSTA-22 | Order all community supplies for programming | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
437 | 124 | LSTA-23 | Order enough for at least 1 quarter of programs |  | 3 Months Prior | 3 | 2025-08-01 17:00 | Life Stages |  | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No | [6 empty] | craft supplies, bingo, baking, exercise, games, puzzles, décor supplies
438 | 124.1 | LSTA-24 | Begin Entertainment programs | Bobbi Olson | 1 Month Prior | 1 | 2025-08-01 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog
439 | 125 | LSTA-25 | Collect W-9s for all entertainers planning on coming to the community |  | 1 Month Prior | 1 | 2025-05-30 17:00 | Life Stages |  | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No
440 | 125.1 | LSTA-26 | Beautyshop Compliance | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
441 | 126 | LSTA-27 | Assure pricing is competitive with market |  | 3 Months Prior | 3 | 2025-07-02 17:00 | Life Stages |  | 20% | Medium | yes | 2025-05-30 09:00 |  |  | 40 hours | 8 hours | 32 hours | 24 days | No
442 | 126.1 | LSTA-28 | Create price list | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
443 | 126.2 | LSTA-29 | work with HSK for SDS compliance | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
444 | 126.3 | LSTA-30 | Review license for state regulations | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
445 | 126.4 | LSTA-31 | Complete contract | Bobbi Olson | 3 Months Prior | 3 | 2025-05-30 17:00 | Life Stages | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
446 | 126.5 | HR-012 | Create Team Member P&P / Handbook before first employee. | Shannon Joyce | 7 Months Prior | 7 | 2025-07-02 17:00 | Human Resources | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Use majority handbook and upload in Paycor and Post on SharePoint
447 | 127 | HR-013 | Coordinate and create all benefit plans for new community with brokers and Paycor, including EDI feeds. | Faith Mong | 7 Months Prior | 7 | 2025-07-02 17:00 | Human Resources | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Health, Dental, Vision, STD, LTD, CI, Life (currently with Highmark, Guardian, VBA, Empower) | Need EIN
448 | 128 | HR-014 | Set up Bonusly Account | Shannon Joyce | 7 Months Prior | 7 | 2025-07-02 17:00 | Human Resources | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Update Paycor roster report for new company to ensure first hire is loaded.
449 | 129 | HR-015 | Establish New Company in Paycor | Shannon Joyce | 7 Months Prior | 7 | 2025-07-02 17:00 | Human Resources | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Initiate process with sales rep. | Need EIN & Voided Check
450 | 130 | HR-016 | Set up applicable tax accounts for new company | Amy Myers | 7 Months Prior | 7 | 2025-07-02 17:00 | Human Resources | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | State & Unemployment and local | Need EIN
451 | 131 | HR-017 | Set up employee insurance policies | Shannon Joyce | 7 Months Prior | 7 | 2025-07-02 17:00 | Human Resources | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Work Comp, EPLI, Cyber (Sales Office??)
452 | 132 | HR-018 | Determine payroll cycle and paydates | Amy Myers | 7 Months Prior | 7 | 2025-07-02 17:00 | Human Resources | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Add into existing cycles based on pay date determined.
453 | 133 | HR-019 | Set overtime rules and pay period dates | Shannon Joyce | 7 Months Prior | 7 | 2025-07-02 17:00 | Human Resources | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Use basline Over 40 rule for all departments unless otherwise specified.
454 | 134 | HR-020 | Set up with recruitment resources (ATS, Indeed, ICC Careers) and include in SRET | Shannon Joyce | 4 Months Prior | 4 | 2025-07-02 17:00 | Human Resources | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | ATS, Indeed, ICC Careers, SRET | Need EIN
455 | 135 | HR-023 | LStaD |  | 3 Months Prior | 3 | 2025-05-30 17:00 | Human Resources |  | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No | [6 empty] | Use existing job descriptions, create any new positions as needed.
456 | 135.1 | HR-040 | Staffing Needs Assessment: Assess the required staff for various departments like administration, nursing, dining, housekeeping, maintenance, etc., based on the size and services offered by the community. | Belinda Mcquaide | 3 Months Prior | 3 | 2025-05-30 17:00 | Operations | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
457 | 136 | HR-042 | Plan/host job fair with onsite team. | Shannon Joyce | 2 Months Prior | 2 | 2025-09-30 17:00 | Human Resources | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 528 hours | 0 hours | 528 hours | 66 days | No |  |  |  | Backlog |  |  | ASD/EOO to choose date, HR to assist with promotion ideas and onsite implementation.
458 | 137 | HR-044 | Team Member Uniforms: Assess and Order | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Coordinate samples for community and work with ASD on placing first order through DSSI.
459 | 138 | HR-045 | Order Name Tags | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Engraved tags for managers, window tags for hourly team members.
460 | 139 | HR-046 | Enter Community into tracking tool / SRET files | James Howell | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Create SRET files and train ASD on tracking.
461 | 140 | HR-047 | Set up Daily Pay Accont | Amy Myers | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Initiate process with sales rep.
462 | 141 | HR-048 | Setup business office with supplies and tools | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Purchase items through DSSI. Faith Mong to review and finalize list. Doug McAnlis to place order for all supplies.
463 | 142 | HR-049 | 1 Navy Blue 3 3-Ring BinderStaples Item #702875 |  | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources |  | 0% | Medium | yes | 2025-01-20 09:00 |  |  | 12896 hours | 0 hours | 12896 hours | 140 days | No | [6 empty] | 1 Navy Blue 3" 3-Ring BinderStaples Item #702875
464 | 142.1 | HR-050 | 1 Green 3 3-Ring BinderStaples Item #892167 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Green 3" 3-Ring BinderStaples Item #892167
465 | 142.2 | HR-051 | 1 Orange 3 3-Ring BinderStaples Item #728073 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Orange 3" 3-Ring BinderStaples Item #728073
466 | 142.3 | HR-052 | 1 Purple 3 3-Ring BinderStaples Item #895621 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Purple 3" 3-Ring BinderStaples Item #895621
467 | 142.4 | HR-053 | 1 Light Blue 3 3-Ring BinderStaples Item #651743 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Light Blue 3" 3-Ring BinderStaples Item #651743
468 | 142.5 | HR-054 | 1 Pink 2 3-Ring BinderStaples Item #651747 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Pink 2" 3-Ring BinderStaples Item #651747
469 | 142.6 | HR-055 | 1 Green 1 3-Ring BinderStaples Item #827602 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Green 1" 3-Ring BinderStaples Item #827602
470 | 142.7 | HR-056 | 1 Black 1 3-Ring BinderStaples Item #648819 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Black 1" 3-Ring BinderStaples Item #648819
471 | 142.8 | HR-057 | 4 White Staples Economy 1/2 3-Ring BinderStaples Item #374818 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 4 White Staples Economy 1/2" 3-Ring BinderStaples Item #374818
472 | 142.9 | HR-058 | 1 Staples Envelopes Tinted #9Staples Item #266759 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Staples Envelopes Tinted #9Staples Item #266759
473 | 142.10 | HR-059 | 1 Staples Envelopes Tinted #8Staples Item #438614 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Staples Envelopes Tinted #8Staples Item #438614
474 | 142.11 | HR-060 | 1 Avery Address LabelsStaples Item #415489 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Avery Address LabelsStaples Item #415489
475 | 142.12 | HR-061 | 3 Safco 3-Pocket Steel Wall FileStaples Item #711454 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 3 Safco 3-Pocket Steel Wall FileStaples Item #711454
476 | 142.13 | HR-062 | 16 Swingline Desktop StaplerStaples Item #504308 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 16 Swingline Desktop StaplerStaples Item #504308
477 | 142.14 | HR-063 | 16 Swingline StaplesStaples Item #108985 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 16 Swingline StaplesStaples Item #108985
478 | 142.15 | HR-064 | 16 Scotch Desktop Tape DispenserStaples Item #567884 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 16 Scotch Desktop Tape DispenserStaples Item #567884
479 | 142.16 | HR-065 | 3 Staples Tape - 12 PackStaples Item #487908 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 3 Staples Tape - 12 PackStaples Item #487908
480 | 142.17 | HR-066 | 3 Staples 2-Hole PuncherStaples Item #799825 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 3 Staples 2-Hole PuncherStaples Item #799825
481 | 142.18 | HR-067 | 16 Staples Circle 3-Hole PunchStaples Item #572645 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 16 Staples Circle 3-Hole PunchStaples Item #572645
482 | 142.19 | HR-068 | 2 Jumbo Paperclips - 10 PackStaples Item #472514 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 Jumbo Paperclips - 10 PackStaples Item #472514
483 | 142.20 | HR-069 | 2 Regular Paperclips - 1000 PackStaples Item #472498 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 Regular Paperclips - 1000 PackStaples Item #472498
484 | 142.21 | HR-070 | 1 Staples Heavyweight Clasp EnvelopesStaples Item #122069 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Staples Heavyweight Clasp EnvelopesStaples Item #122069
485 | 142.22 | HR-071 | 1 Staples EasyClose Catalog EnvelopesStaples Item #379479 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Staples EasyClose Catalog EnvelopesStaples Item #379479
486 | 142.23 | HR-072 | 1 Canon Desktop Printing CalculatorStaples Item #322834 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-01-20 09:00 |  |  | 1120 hours | 0 hours | 1120 hours | 140 days | No |  |  |  | Backlog |  |  | 1 Canon Desktop Printing CalculatorStaples Item #322834
487 | 142.24 | HR-073 | 4 Staples Bond Paper RollStaples Item #531152 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 4 Staples Bond Paper RollStaples Item #531152
488 | 142.25 | HR-074 | 1 Honeywell Drop Box SafeStaples Item #2106798 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Honeywell Drop Box SafeStaples Item #2106798
489 | 142.26 | HR-075 | 1 Paper CutterStaples Item #818674 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Paper CutterStaples Item #818674
490 | 142.27 | HR-076 | 3 8.5 x 11 Copy PaperStaples Item #324791 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 3 8.5" x 11" Copy PaperStaples Item #324791
491 | 142.28 | HR-077 | 1 11 x 17 Copy PaperStaples Item #512215 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 11" x 17" Copy PaperStaples Item #512215
492 | 142.29 | HR-078 | 1 Sentry SafeStaples Item #708268 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Sentry SafeStaples Item #708268
493 | 142.30 | HR-079 | 1 Blue Staples File FolderStaples Item #224527 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Blue Staples File FolderStaples Item #224527
494 | 142.31 | HR-080 | 1 Yellow Staples File FolderStaples Item #224535 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Yellow Staples File FolderStaples Item #224535
495 | 142.32 | HR-081 | 1 Brother Label MakerStaples Item #2244739 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Brother Label MakerStaples Item #2244739
496 | 142.33 | HR-082 | 2 Brother Label Maker TapeStaples Item # | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 Brother Label Maker TapeStaples Item #
497 | 142.34 | HR-083 | 2 BIC Black Pens 60/PackStaples Item #442901 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 BIC Black Pens 60/PackStaples Item #442901
498 | 142.35 | HR-084 | 2 BIC Blue Pens 60/PackStaples Item #031301 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 BIC Blue Pens 60/PackStaples Item #031301
499 | 142.36 | HR-085 | 2 BIC Red Pens - DozenStaples Item #395895 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 BIC Red Pens - DozenStaples Item #395895
500 | 142.37 | HR-086 | 1 Dab N Seal Mail SealerStaples Item #323354 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Dab N Seal Mail SealerStaples Item #323354
501 | 142.38 | HR-087 | 1 Staples Manilla File FoldersStaples Item #221689 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Staples Manilla File FoldersStaples Item #221689
502 | 142.39 | HR-088 | 2 Sticky Notes, Large - 12 PadsStaples Item #576153 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 Sticky Notes, Large - 12 PadsStaples Item #576153
503 | 142.40 | HR-089 | 2 Sticky Notes, Small - 12 PadsStaples Item #105791 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 Sticky Notes, Small - 12 PadsStaples Item #105791
504 | 142.41 | HR-090 | 3 Sharpie Highlighters - AssortedStaples Item #24376663 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 3 Sharpie Highlighters - AssortedStaples Item #24376663
505 | 142.42 | HR-091 | 1 Staples EasyClose #9 EnvelopesStaples Item #570235 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Staples EasyClose #9 EnvelopesStaples Item #570235
506 | 142.43 | HR-092 | 2 BIC WhiteoutStaples Item #483018 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 BIC WhiteoutStaples Item #483018
507 | 142.44 | HR-093 | 1 TRU Red File OrganizerStaples Item #24402468 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 TRU Red File OrganizerStaples Item #24402468
508 | 142.45 | HR-094 | 4 Lightgreen Pressboard FoldersStaples Item #614430 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 4 Lightgreen Pressboard FoldersStaples Item #614430
509 | 142.46 | HR-095 | 4 Staples Hanging FoldersStaples Item #266262 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 4 Staples Hanging FoldersStaples Item #266262
510 | 142.47 | HR-096 | 4 Scissors - 3 PackStaples Item #24403732 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 4 Scissors - 3 PackStaples Item #24403732
511 | 142.48 | HR-097 | 4 Binder Clips - Assorted SizesStaples Item #378813 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 4 Binder Clips - Assorted SizesStaples Item #378813
512 | 142.49 | HR-098 | 2 Staples Note Pads 8.5 x 11.75 WhiteStaples Item #163865 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 Staples Note Pads 8.5" x 11.75" WhiteStaples Item #163865
513 | 142.50 | HR-099 | 2 Staples Notepads 5 x 8Staples Item #814044 replaced | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 Staples Notepads 5" x 8"Staples Item #814044 replaced
514 | 142.51 | HR-100 | 3 Avery 1 Binders - 4 PackStaples Item #24341276 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 3 Avery 1" Binders - 4 PackStaples Item #24341276
515 | 142.52 | HR-101 | 14 Avery A-Z DividersStaples Item #257386 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 14 Avery A-Z DividersStaples Item #257386
516 | 142.53 | HR-102 | 6 Avery Monthly DividersStaples Item #257451 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 6 Avery Monthly DividersStaples Item #257451
517 | 142.54 | HR-103 | 10 Staples Plain DividersStaples Item #462754 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 10 Staples Plain DividersStaples Item #462754
518 | 142.55 | HR-104 | 3 Expo Dry Erase Marker KitStapes Item #24398950 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 3 Expo Dry Erase Marker KitStapes Item #24398950
519 | 142.56 | HR-105 | 1 Cork Bulletin BoardStaples Item #1682310 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 1 Cork Bulletin BoardStaples Item #1682310
520 | 142.57 | HR-106 | 2 Quartet White BoardStaples Item #766220 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 Quartet White BoardStaples Item #766220
521 | 142.58 | HR-107 | 4 Mail Openers - 2 PackStaples Item #815014 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 4 Mail Openers - 2 PackStaples Item #815014
522 | 142.59 | HR-108 | 4 Magnetic Paperclip DispenserStaples Item #216283 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 4 Magnetic Paperclip DispenserStaples Item #216283
523 | 142.60 | HR-109 | 2 Mechanical Pencils - 24 PackStaples Item #1170083 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 Mechanical Pencils - 24 PackStaples Item #1170083
524 | 142.61 | HR-110 | 3 Red Divided Folders - 20/boxStaples Item #614617 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 3 Red Divided Folders - 20/boxStaples Item #614617
525 | 142.62 | HR-111 | 3 Avery File Folder Labels 8366Staples Item # 779330 | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 3 Avery File Folder Labels 8366Staples Item # 779330
526 | 142.63 | HR-112 | 3 Small Rack Insert holder | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 3 Small Rack Insert holder
527 | 142.64 | HR-113 | 5 Large Flyer/Brochure insert holder | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 5 Large Flyer/Brochure insert holder
528 | 142.65 | HR-114 | 2 Easle | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | 2 Easle
529 | 143 | HR-116 | Continued Education and Training: Provide ongoing professional development opportunities to enhance staff skills and knowledge in areas relevant to senior living care. | Larry Rouvelas, Faith Mong | Week of Acquisition | 0 | 2025-09-01 17:00 | Human Resources | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 704 hours | 0 hours | 704 hours | 44 days | No |  |  |  | Backlog |  |  | Regionals to have bi-weekly monthly check-ins with their counter parts on progress of department. These check in are to be scheduled after the new manager starts. Please mark below once your meetings have been scheduled: □Maintenance/Housekeeping □Admi □M
530 | 144 | HR-117 | Onboarding Process: Design an onboarding process that includes orientation, training programs, and introduction to community policies, procedures, and safety protocols. | Shannon Joyce | Week of Acquisition | 0 | 2025-09-01 17:00 | Operations | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 352 hours | 352 hours | 0 hours | 44 days | No |  |  |  | Backlog
531 | 145 | HR-118 | Community Outreach and Networking: Engage with local educational institutions, professional associations, and community organizations to build relationships and pipelines for talent acquisition. | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Faith Mong & Brittany Balouris to source list of local connections and establish contact for recruitment.
532 | 146 | HR-119 | Technology Integration: Implement HR software systems for efficient recruitment, onboarding, payroll, and performance management processes. | James Howell | 7 Months Prior | 7 | 2025-01-31 17:00 | Technology | Not Started | 0% | Medium | yes | 2025-01-31 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  |  | coincide w/ EIN & first hire
533 | 147 | HR-120 | Employee Engagement Initiative: Implement strategies to foster a positive work environment, promote teamwork, and recognize employee contributions. | Faith Mong | 1 Month Prior | 1 | 2025-08-01 17:00 | Human Resources | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Work with onsite ASD & EOO to create initial team member enaggement plans post opening.
534 | 148 | FIN-01 | Review Management Agreement for ICC development fees and pre-opening fee schedules | Maureen Battin | 13 Months Prior | 13 | 2025-07-02 17:00 | Financial Services | Not Started | 0% | Medium | yes | 2025-07-02 08:00 | [5 empty] | 1 day | No |  |  |  | Backlog |  |  | Review with developer if invoicing from ICC is required and timing of payments
535 | 149 | FIN-02 | Review Management Agreement for mgmt fees, consulting fees, financial reporting, etc. | Maureen Battin | 13 Months Prior | 13 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Confirm Mgmt Fee %, Consulting Fee amounts and if escalates each year, date financial reports is required. Review our standard reporting package to confirm it meets their requirements.
536 | 150 | FIN-03 | Retrieve EIN for new entity | Maureen Battin | 8 Months Prior | 8 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Request from Developer
537 | 151 | FIN-04 | Assign Company Code/s and communicate to HR | Maureen Battin | 7 Months Prior | 7 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Update from Copy Machine-Cost Center Codes saved in the Financials Service Handbook General Info folder
538 | 152 | FIN-05 | Set up Bank Accounts and all signers | Maureen Battin | 7 Months Prior | 7 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Contact FNB, Tracie Elza, elzat@fnb-corp.com with legal name, dba name, address, authorized signer, ACH/Wire capability, TMs for access provide TE email. Select next number in sequence | Need EIN
539 | 153 | FIN-06 | Order check stock | Maureen Battin | 7 Months Prior | 7 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Contact Safeguard, Fred Olaharski, fred.ski@verizon.net, with legal name, dba name, billing address as HO, bank routing number and account number, 1 signature line, check # start 1000, color of checks | Need bank acct opened
540 | 154 | FIN-07 | Set up accounting books in Great Plains | Maureen Battin | 7 Months Prior | 7 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Contact Percy Gum, pgum@vertilocity to create a new database in Great Plains for the entity. Need 3 alpha code for community and name, only need chart of accounts copied over, no other information needed (ie F/A, budget) | 1-2 wks for Veritilocity
541 | 155 | FIN-08 | Add community to forms | Faith Richards | 7 Months Prior | 7 | 2025-01-31 17:00 | Financial Services | Not Started | 50% | Medium | yes | 2025-01-31 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog |  |  | Vendor allocation, check requesst, expense report and mileage matrix, remove old version from SharePoint
542 | 156 | FIN-09 | Order remote deposit scanner | Maureen Battin | 6 Months Prior | 6 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Contact FNB, Tracie Elza, elzat@fnb-corp.com to order remote deposit scanner to be delivered directly to the community. | After sales office is open and receiving deposits
543 | 157 | FIN-10 | Set up on-line user access in bank portal for EOO and ASD | Maureen Battin | 6 Months Prior | 6 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | FS team member can set up access on FNB on-line banking (needs Admin access) | Bank account established and hiring of the team member
544 | 158 | FIN-11 | Create W9 for new entity | Maureen Battin | 6 Months Prior | 6 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | add link to W9 form - sample form located on Financial Services HUB - W9 Document folder
545 | 159 | FIN-12 | Record resident deposits in MoveN | Maureen Battin | 6 Months Prior | 6 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Enter deposits as advanced payment, once monthly bank statements are reconciled and are deposits recorded close month in MoveN, can only close one month per day | MoveN AR module activated and deposits being received
546 | 160 | FIN-13 | Communicate process for expense reports and travel policy to community team members | Maureen Battin | 6 Months Prior | 6 | 2025-02-28 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-02-28 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Current forms and policy located at Community HUB - ICC Operations - Forms All | Updated form and hiring of team member
547 | 161 | FIN-14 | Establish P-Card for the community and communicate policy to EOO | Jessica Talak | 6 Months Prior | 6 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Contact Tracie Elza at FNB, elzat@fnb-corp | Hiring of EOO
548 | 162 | FIN-15 | Set up FedEx accounts for the community | Maureen Battin | 6 Months Prior | 6 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | ICC Office Manager has access to establish account
549 | 163 | FIN-16 | Set up Staples account for the community | Jessica Talak | 6 Months Prior | 6 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Can set up individual account but will be part of the DSSI platform | Sales office open
550 | 164 | FIN-17 | Determine FSA to handle community's books | Maureen Battin | 3 Months Prior | 3 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
551 | 165 | FIN-18 | Set up financial reports in Management Reporter | Maureen Battin | 3 Months Prior | 3 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Copy existing reports with new community name as prefix | GP Database needs created
552 | 166 | FIN-19 | Set up Metaviewer/AP Emails | Maureen Battin | 3 Months Prior | 3 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Contact Matt McDowell for establishing AP emails, upon completion contact Metaviewer mvrhelp@metafile.com to create company in Metaviewer, 1-2 wks for Metafile to complete | 1) GP database needs established 2) Matt needs AP email established 3) Metaviewer sets up MV
553 | 167 | FIN-20 | Confirm number of user licenses enough to accomodate new entity | Maureen Battin | 3 Months Prior | 3 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Confirm in Metaviewer User Manager number of licenses available (Jess and Matt have access). To add licenses contact Ryan Wiener Metaviewer at ryan.wiener@metafile.com, sold in packages of 25 users
554 | 168 | FIN-21 | Add new users to Metaviewer and double check access for certain roles | ICC Admin | 3 Months Prior | 3 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  |  | Metaviewer database is set up and TM hired
555 | 169 | FIN-22 | Confirm AP email is forwarding invoices to Metaviewer | ICC Admin | 3 Months Prior | 3 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  |  | Metaviewer database is set up
556 | 170 | FIN-23 | Test scanning ability from printers to Metaviewer (both community and home office) | ICC Admin | 3 Months Prior | 3 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  |  | Metaviewer database is set up
557 | 171 | FIN-25 | Communicate Metaviewer video training to new TeamMembers and timeline for completion | Jessica Talak, Maureen Battin | 1 Month Prior | 1 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 16 hours | 16 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Video is housed in the ICC Training HUB in SharePoint. Training should be as close to opening as possible, too far out and managers cannot apply training to actual | Metaviewer database is set up
558 | 172 | FIN-26 | Set up ACH template in the bank for resident payments | Maureen Battin | 1 Month Prior | 1 | 2025-08-01 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 184 hours | 0 hours | 23 days | No |  |  |  | Backlog |  |  | Refer to set up directions on the Financial Services HUB, Training doc folder - Financial Handbook - 4-Banking&Cash folder | Bank account estabished
559 | 173 | FIN-27 | Complete credit information, to include: bank acct, phone #, addresses, EIN | Maureen Battin | 1 Month Prior | 1 | 2025-08-01 17:00 | Financial Services | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 184 hours | 0 hours | 23 days | No |  |  |  | Backlog |  |  | Saved on Financial Service HUB - Credit App folder
560 | 174 | DIN-01 | Assist in designing kitchen, satelite kitchen, bistros, dining rooms | Bob Scheele | 18 Months Prior | 18 | 2025-07-02 17:00 | Dining | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Work with kitchen designer and development teams
561 | 175 | DIN-02 | Update FF&E list this includes kitchen utensils, dining room needs | Bob Scheele | 6 Months Prior | 6 | 2025-02-28 17:00 | Dining | Not Started | 100% | Medium | yes | 2025-02-28 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Update according to what programs are available and budget
562 | 176 | DIN-03 | Provide specs to contractor on coffee machines and juice dispensers | Bob Scheele | 12 Months Prior | 12 | 2025-07-02 17:00 | Dining | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | This includeds electrical and plumbing
563 | 177 | DIN-04 | Inform primary food vendor of new build project | Bob Scheele | 12 Months Prior | 12 | 2025-01-01 17:00 | Dining | In progress | 100% | Medium | yes | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Info provided so that team can start planning delivery routes, delivery days etc…
564 | 178 | DIN-05 | Grease trap cleaning contract secured | Bob Scheele | 3 Months Prior | 3 | 2025-05-30 17:00 | Dining | In progress | 100% | Medium | yes | 2025-05-30 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | needed for CofO
565 | 179 | DIN-06 | Exhaust hood cleaning contract secured | Bob Scheele | 3 Months Prior | 3 | 2025-05-30 17:00 | Dining | In progress | 100% | Medium | yes | 2025-05-30 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | needed for CofO
566 | 180 | DIN-07 | Trash and recycling removal contracts secured | Bob Scheele | 3 Months Prior | 3 | 2025-05-30 17:00 | Dining | Done | 100% | Medium | yes | 2025-05-30 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | needed for CofO
567 | 181 | DIN-08 | DSSI platform set up | Bob Scheele | 2 Months Prior | 2 | 2025-07-01 17:00 | Dining | In progress | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | useful for ordering pre-opening items from vendors.
568 | 182 | DIN-09 | Inform HPSI of new build | Bob Scheele | 2 Months Prior | 2 | 2025-07-01 17:00 | Dining | In progress | 100% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
569 | 183 | DIN-10 | Create Vendor Accounts | Bob Scheele | 6 Months Prior | 6 | 2025-02-28 17:00 | Dining | Not Started | 0% | Medium | yes | 2025-02-28 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Work with HPSI to ensure all pertinent info is provided to all vendors under the program | Bank acct #, address, phone #, EIN #, LLC info, etc. provided by Financial Services
570 | 184 | DIN-11 | Walk through of kitchen equipment install | Bob Scheele | 3 Months Prior | 3 | 2025-05-30 17:00 | Dining | Next up | 0% | Medium | yes | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Validate all major kitchen equipment in place and operable, no damage | Kitchen install complete
571 | 185 | DIN-12 | Coordinate install of soap dispensers | Bob Scheele | 1 Month Prior | 1 | 2025-08-01 17:00 | Dining | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | Work with Innoserve to have dispensers installed and operable. Scope includes: dish machine(s), pot sinks, and mop closets
572 | 186 | DIN-13 | Hand Sink soap dispensers and towel dispensers install | Paul Martin | 1 Month Prior | 1 | 2025-08-01 17:00 | Dining | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 184 hours | 0 hours | 184 hours | 23 days | No |  |  |  | Backlog |  |  | CWP install pre C of O.
573 | 187 | DIN-14 | Orient TMs to kitchen equipment | Bob Scheele | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | At one week out, kitchen equipment reps on site to train cooking team. Warranties go into affect on this day, equipment binders given to Dining Service and SME. All equipment is turned on and operating this day including coolers,freezer, stove, ovens. Tra | Hourly TMS hired
574 | 188 | DIN-15 | Kitchen equipment reps on site to train hourly team |  | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining |  | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 1408 hours | 0 hours | 1408 hours | 44 days | No
575 | 188.1 | DIN-16 | Distribute equipment binders to DED & SME | Bob Scheele | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog
576 | 188.2 | DIN-17 | Confirm kitchen equipment is turned on & operational | Bob Scheele | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | Includes: coolers, freezer, stove, ovens
577 | 188.3 | DIN-18 | Train FS hourly TMs on use & maintenance of equipment | Bob Scheele | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  |  | Hourly TMS hired
578 | 188.4 | DIN-19 | Smallwares, china, unpacked, washed, put away | Bob Scheele | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | 2 weeks out | DS install complete
579 | 189 | DIN-20 | Create Vendor Accounts | Bob Scheele | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | if using smaller local vendors, set up accounts at 2 weeks out
580 | 190 | DIN-21 | Kitchen deep cleaned | Bob Scheele | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | At 1 weeks out, sanitize all equipment, shelving, racks, carts, surfaces that have been in contact with construction dust and debris. | Construction team no longer actively working in the building
581 | 191 | DIN-22 | Confirm coffee makers and juice machines delivered, installed, & operable | Bob Scheele | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog
582 | 192 | DIN-23 | Initial food order and emergency food supplies | Bob Scheele | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog
583 | 193 | DIN-24 | Place initial food order |  | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining |  | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 712 hours | 0 hours | 712 hours | 45 days | No | [6 empty] | This is a large order of food and non food items that are staples needed to operate dept. Order gets placed roughly 5 days out from IL residents moving in
584 | 193.1 | DIN-25 | Unpack initial food delivery and put into place | Bob Scheele | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | This is a large undertaking ensuring items are placed in logical spaces, and dated
585 | 193.2 | DIN-26 | Emergency Food supplies on separate rack or in separate room labled as emergency | Bob Scheele | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog
586 | 193.3 | DIN-27 | Train DED | Bob Scheele | 2 Months Prior | 2 | 2025-07-01 17:00 | Dining | Not Started | 0% | Medium |  | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | COSM, End of Month report, Menu2U, all basics about operation the department. | DED must be hired
587 | 194 | DIN-28 | Train initial hourly hires | Bob Scheele | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | 2 cooks, at least 2 pt servers depending on IL/AL community. Training should occur at one week out
588 | 195 | DIN-29 | Create menus | Bob Scheele | 2 Months Prior | 2 | 2025-07-01 17:00 | Dining | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Work with DED to revise corporate menu | Computer needed for DED
589 | 196 | DIN-30 | Add property to Menu2U | Bob Scheele | 2 Months Prior | 2 | 2025-07-01 17:00 | Dining | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
590 | 197 | DIN-31 | Add property to existing departmental forms | Bob Scheele | Week of Acquisition | 0 | 2025-09-01 17:00 | Dining | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | Food temp sheets, Cooler and Freezer temp sheets, Dish machine temp sheets,
591 | 198 | DIN-32 | Train DED on use and filing of Department regulatory forms. | Bob Scheele | 2 Months Prior | 2 | 2025-07-01 17:00 | Dining | Not Started | 0% | Medium | yes | 2025-07-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
592 | 199 | Dev-001 | Open sales center | Sarah Spardy | 12 Months Prior | 12 | 2025-01-01 17:00 | Development | Not Started | 100% | Medium | yes | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Scope of work to include, but not limited to: determining location, securing lease/trailer rental, set up of temporary utilities, making any necessary cosmetic improvements (to be negotiated with landlord), providing renderings & other marketing materials
593 | 200 | Dev-002 | Determine sales center location |  | 12 Months Prior | 12 | 2025-07-02 17:00 | Development |  | 46% | Medium | yes | 2025-01-01 09:00 |  |  | 400 hours | 184 hours | 216 hours | 131 days | No | [6 empty] | Looking for 12 month lease w/ intent to have 6 months out from C of O; if we can't find rental space need to pursue using a trailer or some other creative solution
594 | 200.1 | Dev-003 | Sign sales center lease | Sarah Spardy | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | if we do a 1 year lease, 3 months to get it ready, 6 months to C of O, 3 month cushion to allow for construction delays
595 | 200.2 | Dev-004 | Send out press release re: opening of sales center | Larry Rouvelas | 9 Months Prior | 9 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  |  | lease signed
596 | 200.3 | Dev-005 | Send sales center layout to Aptura for space design and furniture selection | Sarah Spardy | 11 Months Prior | 11 | 2025-01-01 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
597 | 200.4 | Dev-006 | Evaluate sales center space for improvements | Sarah Spardy | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | is it accessible, does it need painted, does it need cleaned, parking lot, landscaping, etc | lease signed
598 | 200.5 | Dev-007 | Weather dependent: set thermostat in sales center to reasonable temp so pipes don't freeze | Sarah Spardy | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  |  | lease signed
599 | 200.6 | Dev-008 | Establish sales center utilities | John Stare | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Determine if we will reimburse landlord (preferred) or set up in our name
600 | 200.7 | Dev-009 | Set up sales center electric | John Stare | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
601 | 200.8 | Dev-010 | Set up sales center heating oil/fuel | John Stare | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
602 | 200.9 | Dev-011 | Set up sales center trash pickup | John Stare | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
603 | 200.10 | Dev-012 | Set up sales center snow removal contract | John Stare | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Weather dependent
604 | 200.11 | Dev-013 | Set up sales center landscaping contract | John Stare | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
605 | 200.12 | Dev-014 | Set up sales center water | John Stare | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
606 | 200.13 | Dev-015 | Schedule black water removal at sales center | John Stare | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | if trailer being utilized
607 | 200.14 | Dev-016 | Set up sales center internet | John Stare | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | typically comcast
608 | 200.15 | Dev-017 | Order sales center phones | John Stare | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Work with Advent on package for the entire building, and pull out the phones specifically needed for install at the sales center; include hold music in contract
609 | 200.16 | Dev-018 | Establish sales center phone # | John Stare | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Frankel
610 | 200.17 | Dev-019 | Obtain directional signage for sales center | Larry Rouvelas | 8 Months Prior | 8 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | sandwich boards, building signage, temporary wire signs
611 | 200.18 | Dev-020 | Obtain design boards & renderings from interior designer for sales center | Sarah Spardy | 8 Months Prior | 8 | 2025-01-01 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
612 | 200.19 | Dev-021 | Compile marketing materials for on-site team at sales center | Sarah Spardy | 7 Months Prior | 7 | 2025-01-31 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Building renderings, unit renderings (3dplans.com), clean set of building floorplans, construction photos, boards from Aptura, fact sheet (similar to what we used at groundbreaking), detail on common area & amenities offered, sample menu, sample activity
613 | 200.20 | Dev-022 | Building renderings | Sarah Spardy | 7 Months Prior | 7 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
614 | 200.21 | Dev-023 | Unit renderings | Sarah Spardy | 7 Months Prior | 7 | 2025-01-31 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | 3dplans.com
615 | 200.22 | Dev-024 | Minimal set of floorplans | Sarah Spardy | 7 Months Prior | 7 | 2025-01-31 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | 2 sets: colored & uncolored
616 | 200.23 | Dev-025 | Construction photos | Sarah Spardy | 7 Months Prior | 7 | 2025-01-31 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
617 | 200.24 | Dev-026 | Design boards | Sarah Spardy | 7 Months Prior | 7 | 2025-01-31 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | typically from Aptura; these will be called out in the interior design contract
618 | 200.25 | Dev-027 | Fact sheet | Sarah Spardy | 7 Months Prior | 7 | 2025-01-31 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | should have carryover materials from groundbreaking
619 | 200.26 | Dev-028 | Detail on common areas & amenities offered | Sarah Spardy | 7 Months Prior | 7 | 2025-01-31 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
620 | 200.27 | Dev-029 | Sample menu | Megan Campbell | 7 Months Prior | 7 | 2025-01-31 17:00 | Operations | Not Started | 0% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
621 | 200.28 | Dev-030 | Sample activity program (all 3 levels) | Bobbi Olson | 7 Months Prior | 7 | 2025-01-31 17:00 | Operations | Not Started | 0% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
622 | 200.29 | Dev-031 | Sample residency documents | Megan Campbell | 7 Months Prior | 7 | 2025-01-31 17:00 | Operations | Not Started | 50% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog
623 | 200.30 | Dev-032 | TV programming guide (ie channels available), | Bobbi Olson | 7 Months Prior | 7 | 2025-01-31 17:00 | Operations | Not Started | 0% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
624 | 200.31 | Dev-033 | List of amenities and providers and what's included in the base rate | Megan Campbell | 7 Months Prior | 7 | 2025-01-31 17:00 | Operations | Not Started | 0% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
625 | 200.32 | Dev-034 | Competitive analysis | Larry Rouvelas | 7 Months Prior | 7 | 2025-01-31 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
626 | 200.33 | Dev-035 | Proposed rates | Larry Rouvelas | 7 Months Prior | 7 | 2025-01-31 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
627 | 200.34 | Dev-036 | Summary outlining levels of care and our point system | Megan Campbell | 7 Months Prior | 7 | 2025-01-31 17:00 | Operations | Not Started | 50% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 4 hours | 4 hours | 1 day | No |  |  |  | Backlog
628 | 200.35 | Dev-037 | Construction timeline | Sarah Spardy | 7 Months Prior | 7 | 2025-01-31 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
629 | 200.36 | Dev-038 | Description of the building | Sarah Spardy | 7 Months Prior | 7 | 2025-01-31 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
630 | 200.37 | Dev-039 | Compile documents/images to be shown on Sales center TV | Larry Rouvelas | 7 Months Prior | 7 | 2025-01-31 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-31 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | floor plans, unit layouts, construction photos, timelapse/drone footage, sample menus (dining & activities) | Sales center TV installed
631 | 200.38 | Dev-040 | obtain sales center FFE | Sarah Spardy | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
632 | 200.39 | Dev-041 | sales center copier | Maureen Battin | 8 Months Prior | 8 | 2025-01-01 17:00 | Procurement | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Precision - this is the big one that gets moved to the work room
633 | 200.40 | Dev-042 | sales center computers | ICC Admin | 6 Months Prior | 6 | 2025-02-28 17:00 | Technology | Not Started | 0% | Medium |  | 2025-02-28 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | confirm w/ Matt: he may get notification to set these up and get in appropriate persons hands once they are hired
634 | 200.41 | Dev-043 | sales center furnishings | Sarah Spardy | 9 Months Prior | 9 | 2025-01-01 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Aptura to provide office furniture, artwork, accessories, conference table, etc
635 | 200.42 | Dev-044 | sales center building transfer appliances | Sarah Spardy | 9 Months Prior | 9 | 2025-01-20 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-20 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | fridge, microwave, TV
636 | 200.43 | Dev-045 | Purchase small appliances for sales center | Bobbi Olson | 6 Months Prior | 6 | 2025-01-20 17:00 | Operations | Not Started | 0% | Medium |  | 2025-01-20 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | keurig, water jug, etc
637 | 200.44 | Dev-046 | Purchase finishing touches for sales center | Bobbi Olson | 6 Months Prior | 6 | 2025-01-20 17:00 | Operations | Not Started | 0% | Medium |  | 2025-01-20 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Small plants for outdoors, anything needed after FF&E/furnishings install
638 | 200.45 | Dev-047 | obtain sales office smallwares | Sarah Spardy | 9 Months Prior | 9 | 2025-01-20 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-20 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
639 | 200.46 | Dev-048 | copy keys for sales center | Sarah Spardy | 9 Months Prior | 9 | 2025-01-20 17:00 | Development | Not Started | 100% | Medium |  | 2025-01-20 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | 3 sets of keys total: John, Kevin, on-site team
640 | 200.47 | Dev-049 | purchase vacuum for sales center | Bobbi Olson | 8 Months Prior | 8 | 2025-01-01 17:00 | Procurement | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | vacuum (to be transferred to the building)
641 | 200.48 | Dev-050 | Purchase walk off mat(s) w/ logo for sales center | Bobbi Olson | 7 Months Prior | 7 | 2025-01-01 17:00 | Marketing | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog
642 | 200.49 | Dev-051 | purchase misc. smallwares for sales center | Bobbi Olson | 6 Months Prior | 6 | 2025-01-01 17:00 | Operations | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | paper products (plates, cups, napkins, toilet paper, paper towels, cleaning supplies, etc)
643 | 200.50 | Dev-052 | Establish cadence for reporting out to ownership group | Sarah Spardy | 9 Months Prior | 9 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Kevin to review with Belinda/AGM
644 | 201 | Dev-053 | Add project to New Development Pipeline page in SharePoint | Sarah Spardy | 16 Months Prior | 16 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Include Project name, location, unit mix, expected delivery date, sales center address/open date, future property address (once established). Locate in the Dev & Acq HUB | Add once project has been funded and/or groundbreaking is scheduled
645 | 202 | Dev-054 | Create project specific Development & Construction page | Sarah Spardy | 13 Months Prior | 13 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Include a countdown timer and area for uploading and refreshing construction photos. Locate in the Dev & Acq HUB.
646 | 203 | Dev-056 | Relocate project folder to Home Office section of Sharepoint | Sarah Spardy | 14 Months Prior | 14 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Move the project folder from Development (Internal) > Development to Home Office (Internal). The Ops team will refer to the building by the name we've come up with, not the geographic location, so rename the folder to what the group will call it. | once construction starts
647 | 204 | Dev-060 | Establish property address | Sarah Spardy | 18 Months Prior | 18 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Typically the devleoper will take the lead on this. ICC to work with developer & local municipality to determine and record the property address.
648 | 205 | Dev-061 | Prepare Executive Summary | Sarah Spardy | 13 Months Prior | 13 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Include key information such as property name, address, developer, debt/equity sponsors, unit mix, key common areas or other selling features, timing, etc
649 | 206 | Dev-062 | Establish pre-opening accounts payable process | Sarah Spardy | 16 Months Prior | 16 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
650 | 207 | Dev-063 | Review payables process with developer |  | 16 Months Prior | 16 | 2025-07-02 17:00 | Development |  | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 24 hours | 24 hours | 0 hours | 1 day | No
651 | 207.1 | Dev-064 | Set up folder on community HUB | Sarah Spardy | 16 Months Prior | 16 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
652 | 207.2 | Dev-065 | Set up expense tracking workbook | Sarah Spardy | 16 Months Prior | 16 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
653 | 207.3 | Dev-066 | Create operations budget | Sarah Spardy | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
654 | 208 | Dev-067 | Dynamic Pricing support workbook |  | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations |  | 96% | Medium | yes | 2025-07-02 08:00 |  |  | 360 hours | 352 hours | 8 hours | 1 day | No
655 | 208.1 | Dev-068 | Create the dynamic pricing support workbook for the new building | James Howell | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | save to budget section of IT HUB | Dynamic pricing support workbook created
656 | 208.2 | Dev-069 | Move-Ins | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Model lease up by program | Dynamic pricing support workbook created
657 | 208.3 | Dev-070 | Rent | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Model existing resident rent and increases and street-rate increases | Dynamic pricing support workbook created
658 | 208.4 | Dev-071 | Price sheet | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Upload unit inventory and market rates | Dynamic pricing support workbook created
659 | 208.5 | Dev-072 | Care | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Update LOC | Dynamic pricing support workbook created
660 | 208.6 | Dev-073 | Increases & 2ndP | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Plug in rates for existing and street rates | Dynamic pricing support workbook created
661 | 208.7 | Dev-074 | Concession | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Enter any existing concessions and model future allowances | Dynamic pricing support workbook created
662 | 208.8 | Dev-075 | Wages & Budgets support workbook | Sarah Spardy | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
663 | 208.9 | Dev-076 | Create the wages & budgets support workbook for the property | James Howell | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | save to budget section of IT HUB | Wages & Budgets workbook created
664 | 208.10 | Dev-077 | Property-specific norms | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | add community and set up expectations | Wages & Budgets workbook created
665 | 208.11 | Dev-078 | For EOOs-AGMs | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | review individual employees for wage adjustments | Wages & Budgets workbook created
666 | 208.12 | Dev-079 | Entry-level wages | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | review/update | Wages & Budgets workbook created
667 | 208.13 | Dev-080 | Community expense workbook | Sarah Spardy | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
668 | 208.14 | Dev-081 | update HO workbook to include the new property | James Howell | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
669 | 208.15 | Dev-082 | Create community expense workbook | James Howell | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
670 | 208.16 | Dev-083 | Develop marketing budget | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Include all 4 accounts: contracted services, collaterals, community, and direct mail | Community expense workbook created
671 | 208.17 | Dev-084 | Develop detailed plan for HO-driven marketing spend | Larry Rouvelas | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Include all 4 accounts: contracted services, collaterals, community, and direct mail | Community expense workbook created
672 | 208.18 | Dev-085 | Develop detailed plan for Community-driven marketing spend | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Include all 4 accounts: contracted services, collaterals, community, and direct mail | Community expense workbook created
673 | 208.19 | Dev-086 | Develop bonus budget | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 0% | Medium |  | 2025-07-02 08:00 | [5 empty] | 1 day | No |  |  |  | Backlog |  |  |  | Community expense workbook created
674 | 208.20 | Dev-087 | Develop detailed plan for HO-driven bonus spend | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Including, at a minimum: CRISP, OBS, CLD/CRD, and new-hires | Community expense workbook created
675 | 208.21 | Dev-088 | Develop detailed plan for Community-driven bonus spend | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Including, at a minimum: EOO discretionary bonus | Community expense workbook created
676 | 208.22 | Dev-089 | Develop seminars/conferences budget | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  |  | Community expense workbook created
677 | 208.23 | Dev-090 | Develop detailed plan for HO-driven seminars/conferences spend | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Including, at a minimum: ICC Leadership conference (if occuring during the current calendar year) | Community expense workbook created
678 | 208.24 | Dev-091 | Develop detailed plan for community-driven seminars/conferences spend | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Including, at a minimum: Admin credits (PHCA), Diabetic training (Marsha Johnson), Servsafe, CPR, SLU, quarterly meetings for each department - 2x in person + 2x virtual | Community expense workbook created
679 | 208.25 | Dev-092 | Develop contracted services/leases budget | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  |  | Community expense workbook created
680 | 208.26 | Dev-093 | Develop detailed plan for HO-driven contracted services/leases spend | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Including, at a minimum: MoveN fees: quarterly user licenses, annual upgrade/tech support, quarterly marketing automation; TELS; DSSI; Menu2u | Community expense workbook created
681 | 208.27 | Dev-094 | Develop detailed plan for community-driven contracted services/leases spend | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Including, at a minimum: Trash & recycling, medical waste, landscaping, snow removal, annual fire inspection, elevator inspection, network support, dire extinguisher & alarms, HVAC PM, hoos & duct cleaning, grease trap, window cleaning, generator, pest co | Community expense workbook created
682 | 208.28 | Dev-095 | Develop employee recognition budget | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  |  | Community expense workbook created
683 | 208.29 | Dev-096 | Develop detailed plan for HO-driven employee recognition spend | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Including, at a minimum: Bonusly, Christmas gifts, annual service recognition (meal at $15/person, pins & certificates), Car party (car + prizes), summer gifts | Community expense workbook created
684 | 208.30 | Dev-097 | Develop detailed plan for community-driven employee recognition spend | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Including, at a minimum: FUN committee, MAP graduation, departmental honoree weeks (Nursing, Housekeeping, Dining, Activities, Admin professionals), monthly t-shirts/gifts/gift cards, NALW week, summer picnic, Christmas party, car party | Community expense workbook created
685 | 208.31 | Dev-098 | Develop operations supply budget | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  |  | Community expense workbook created
686 | 208.32 | Dev-099 | Develop detailed plan for community-driven operations supply spend | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Budget PRD by department | Community expense workbook created
687 | 208.33 | Dev-100 | Develop IL Programming budget | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  |  | Community expense workbook created
688 | 208.34 | Dev-101 | Develop detailed plan for community-driven operations supply spend | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Including, at a minimum: TM appreciation, Carden club, Clubs & committees, IL ambassador, prizes for resident-led games, newsletter and res. Handbook, treasurer, seasonal decorations, live entertainment, continuing education, civic leadership awards, outi | Community expense workbook created
689 | 208.35 | Dev-102 | Develop computer exense budget | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  |  | Community expense workbook created
690 | 208.36 | Dev-103 | Develop detailed plan for HO-driven computer expense spend | James Howell | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Including, at a minimum: IT support (MRM), BI dev & hosting (Evident), internet provider, Accounting GP & AP (Vertilocity and Metafile), Netwrok/wifi management, Sharepoint & security consulting, Microsoft licensing & Hosting | Community expense workbook created
691 | 208.37 | Dev-104 | Develop detailed plan for community-driven computer expense spend | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Anything not included in the HO-driven spend; does not include actual equipment, that goes through cap ex | Community expense workbook created
692 | 208.38 | Dev-105 | Complete operating budget | Sarah Spardy | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
693 | 208.39 | Dev-106 | Create budget file | James Howell | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Set up budget file and back-end connections to appropriate property
694 | 208.40 | Dev-107 | Review and update AIN assumptions not provided by support workbooks | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | fixed/variable staffing, fixed/variable expenses,below the line expenses | Budget file created
695 | 208.41 | Dev-108 | Coordinate review w/ senior management | Sarah Spardy | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | COO, AGM, EOO, Wes, Sarah | All support workbooks and budget file reviews have been completed
696 | 208.42 | Dev-109 | Compare results to proforma | Sarah Spardy | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | How do NOI, leaseup, breakeven, revenues & expenses to what was originally provided to the developer, lender, and owners?
697 | 208.43 | Dev-110 | Present budget to owners | Belinda Mcquaide | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  |  | Budget must be finalized
698 | 208.44 | Dev-111 | Lockdown budget | Sarah Spardy | 4 Months Prior | 4 | 2025-07-02 17:00 | Operations | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  |  | Owners approved budget
699 | 208.45 | Dev-112 | Import budget in to GP | Maureen Battin | 4 Months Prior | 4 | 2025-07-02 17:00 | Financial Services | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  |  | Budget approved by owners; GP database set up
700 | 208.46 | Dev-113 | Determine project name | Sarah Spardy | 18 Months Prior | 18 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog
701 | 209 | Dev-114 | Complete research on site & local history |  | 18 Months Prior | 18 | 2025-07-02 17:00 | Development |  | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 24 hours | 24 hours | 0 hours | 1 day | No | [6 empty] | Does the site have a history that is meaningful within the community (ie Fitz Farm)? Is there a landmark - physical or geographic - we want to honor? Does the street/area we're located have a positive or negative connotation within the community?
702 | 209.1 | Dev-115 | Determine if the project fits in with an existing ICC brand | Sarah Spardy | 18 Months Prior | 18 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | The Residence at….Colonial Courtyard at….etc
703 | 209.2 | Dev-116 | Complete internet searches on proposed name | Sarah Spardy | 18 Months Prior | 18 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Are there other projects with this name? What are the hits that come up when searching the name? If negative associations, can we combat them?
704 | 209.3 | Dev-117 | Determine accent wall colors for Independent Living units | Sarah Spardy | 6 Months Prior | 6 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Consult w/ interior designer to narrow down 4-5 paint colors that we want to offer as an optional accent wall color in our IL units. Once colors have been selected, pull swatches together for display in sales center.
705 | 210 | Dev-118 | Purchase start up supply of accent color paint for IL units | Bobbi Olson | 1 Month Prior | 1 | 2025-07-02 17:00 | Development | Not Started | 100% | Medium | yes | 2025-07-02 09:00 |  |  | 8 hours | 8 hours | 0 hours | 1 day | No |  |  |  | Backlog |  |  | Purchase no later than C of O ; **need to decide what our standard is for start up supply** | need to be able to store in the building
706 | 211 | Dev-119 | Determine TrueDoor options for Life Stories units | Sarah Spardy | 6 Months Prior | 6 | 2025-02-28 17:00 | Development | Not Started | 0% | Medium | yes | 2025-02-28 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Work w/ interior designer to short list the # of design from the 100s available on their site; pallette should work with the scheme decided for the Life Stories neighborhood. | Resident doors must be compatible with TrueDoor product
707 | 212 | Dev-120 | Purchase initial inventory of TrueDoor options | Sarah Spardy | Week of Acquisition | 0 | 2025-09-01 17:00 | Development | Not Started | 0% | Medium | yes | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | Plan to have the order in by C of O; (we still need to determine what the leadtime is on this). Once delivered, we can have Kevin Lewis do the install | need to be able to store in the building
708 | 213 | Dev-121 | Coordinate specialty design elements | Sarah Spardy | 8 Months Prior | 8 | 2025-01-01 17:00 | Development | Not Started | 0% | Medium | yes | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | In prior projects this has included: coordination of monument sign (work w/ GC), custom interior signage in key areas of the building (salon, theater, pub/bistro, LifeStories neighborhood), putting green, piano, lockers, etc
709 | 214 | HR-000 | Hire Management Team |  | 8 Months Prior | 8 | 2025-09-01 17:00 | Human Resources |  | 17% | Medium | yes | 2025-01-01 09:00 |  |  | 1336 hours | 224 hours | 1112 hours | 174 days | No | [6 empty] | See each subtask's description for more detail on when to start recruiting, and target salary.
710 | 214.1 | HR-011 | recruit/hire LifeStories dir | Butch Cassiday Jr | Week of Acquisition | 0 | 2025-09-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | Assumptions 60 day recruitment window This task's due date is the LSD's target start date Start date is 1 pay period prior to assumed receipt of licenselicense is assumed to be received 60 days after receipt of C of O Approved starting salary:$xx
711 | 214.2 | HR-010 | recruit/hire RWD | Butch Cassiday Jr | Week of Acquisition | 0 | 2025-09-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | Assumptions 60 day recruitment window This task's due date is the RWD's target start date Start date is 1 month prior to assumed receipt of licenselicense is assumed to be received 60 days after receipt of C of O Approved starting salary:$xx
712 | 214.3 | HR-009 | recruit/hire LifeStages dir (PC/AL-focus) | Butch Cassiday Jr | Week of Acquisition | 0 | 2025-09-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-07-02 09:00 |  |  | 352 hours | 0 hours | 352 hours | 44 days | No |  |  |  | Backlog |  |  | Assumptions 60 day recruitment window This task's due date is the LSD's target start date Start date is 1 month prior to assumed receipt of licenselicense is assumed to be received 60 days after receipt of C of O Approved starting salary:$xx
713 | 214.4 | HR-008 | recruit/hire Exec Hskpr | Butch Cassiday Jr | 3 Months Prior | 3 | 2025-05-30 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Assumptions 60 day recruitment window This task's due date is the HEA's target start date Start date is 6 weeks out from end of construction/receipt of certificate of occupancy Approved starting salary:$xx
714 | 214.5 | HR-007 | recruit/hire DED | Butch Cassiday Jr | 3 Months Prior | 3 | 2025-05-30 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Assumptions 60 day recruitment window This task's due date is the DED's target start date Start date is 6 weeks out from end of construction/receipt of certificate of occupancy Approved starting salary:$xx
715 | 214.6 | HR-005 | recruit/hire IL director | Butch Cassiday Jr | 3 Months Prior | 3 | 2025-05-30 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Assumptions 60 day recruitment window This task's due date is the IL director's target start date Start date is 6 weeks out from end of construction/receipt of certificate of occupancy Approved starting salary:$xx
716 | 214.7 | HR-004 | recruit/hire ASD | Butch Cassiday Jr | 3 Months Prior | 3 | 2025-05-30 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Assumptions 60 day recruitment window This task's due date is the ASD's target start date Start date is 6 weeks out from end of construction/receipt of certificate of occupancy Approved starting salary:$xx
717 | 214.8 | HR-001 | recruit/hire 1st marketer (IL-focus) | Butch Cassiday Jr | 8 Months Prior | 8 | 2025-01-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Assumptions 60 day recruitment window This task's due date is the marketer's target start date Start date is 6 months out from end of construction/receipt of certificate of occupancy Approved starting salary:$xxPLUS whatever they're eligible to earn with
718 | 214.9 | HR-002 | recruit/hire EOO | Butch Cassiday Jr | 8 Months Prior | 8 | 2025-01-01 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-01-01 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Assumptions 60 day recruitment window This task's due date is the EOO's targeted start date Start date is 6 months out from end of construction/receipt of certificate of occupancy Approved starting salary:$xxPLUS whatever they're eligible to earn with mov
719 | 214.10 | HR-006 | recruit/hire SME | Butch Cassiday Jr | 3 Months Prior | 3 | 2025-05-30 17:00 | Human Resources | Not Started | 0% | Medium |  | 2025-05-30 09:00 |  |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Backlog |  |  | Assumptions 60 day recruitment window This task's due date is the SME's target start date Start date is 6 weeks out from end of construction/receipt of certificate of occupancy Approved starting salary:$xx
720 | 214.11 |  | Determine community's postage machine needs | Jessica Talak |  |  | 2025-08-08 17:00 |  | Not Started | 100% | Medium |  | 2025-07-02 09:00 |  |  | 224 hours | 224 hours | 0 hours | 28 days | No |  |  |  | Backlog